World Food Programme

A Report from the    Office of Evaluation

Evaluation of WFP’s Assistance to China (1979-2005) - Full Report

Rome, December 2005

Ref. OEDE/2006/3

Acknowledgement

This document was prepared by the mission team leader on the basis of preparatory studies and a mission to China (7-28 May 2005).

On behalf of the team, the team leader wishes to express its appreciation to all those who facilitated the team’s work in the field, especially the Project Management Offices of the Government of China, the staff seconded to the WFP CO in Beijing from the Governments of China and Australia, and in the Headquarters.

Responsibility for the content and presentation of findings and recommendations rests with the authors. The views and opinions expressed in the report do not necessarily correspond to the views of WFP, the recipient Government or the cooperating partners.

Mission Composition

- Gilbert Landart, Team Leader, FAO

- Sylvie Dideron, Consultant

- Henri Loze, Consultant

- Cui Shuli, Consultant

- Pernille Hougesen, Evaluation Manager, Office of Evaluation, WFP

- Celso Murano Del Picchia, Researcher

Acronyms

ACWF			All China Women’s Federation

AWPB			Annual Work Plan and Budget

CICETE			China International Centre for Economic and Technical Exchange

CNY			Chinese Yuan (RMB)

CO				Country Office

CP				Country Programme

EDP			WFP Enabling Development Policy

FAO			Food and Agriculture Organization of the United Nations

FFA			Food for Assets

FFT				Food-for-Training

FFW			Food-for-Work

GAD			Gender-and-Development

GFP			Gender Focal Point

GOC			Government of China

IAD				Integrated Agricultural Development

IFAD			International Fund for Agricultural Development

IRD				Integrated Rural Development

M&E			Monitoring and Evaluation

MOA			Ministry of Agriculture

mt				metric tons

O&M			Operations and Maintenance

PLG			Project Leading Group

PMO			Project Management Office

PRA			Participatory Rural Appraisal

RCC			Rural Credit Cooperative

RMB			Renminbi (CNY)

TOR			Terms of Reference

US$				United States Dollar

VAM			Vulnerability Analysis and Mapping

VDP			Village Development Plan

VIG				Village Implementing Group

WCB			Water Conservancy Bureau

WF				Women’s Federation

WID			Women-in-Development

Currency Equivalents (June 2005)

Currency Unit	= Yuan (CNY)

US$1.00	= CNY 8.27

CNY 1.00	= US$0.12

Weights and Measures

1 ha	= 15 mu

1 mu	= 0.066 ha

1 mu	= 667 m2

1 kg	= 2 jin

1 jin	= 0.5 kg

Table of Contents

Executive Summary	vii

1.	Introduction	 1

Purpose and Scope of the Evaluation	 1

Methodology	 1

2.	Review and Assessment of WFP’s 21 Years in China	 2

A.	Evolution of WFP’s Assistance to China (1979-2000)	 2

B.	Conclusions on WFP’s Assistance to China (1979–2000)	 4

B.1  	Overall Assessment	 4

Use and Role of Food Aid	 4

Physical Achievements	 4

Impact on Household Food Security	 4

Sustainability	 5

B.2		Sectoral Development	 5

Overview	 5

Irrigation and Drainage	 6

Economic Impact	 6

Sustainability	 7

Rainfed Agriculture	 7

Erosion Control	 7

Impact on Household Income	 7

Fisheries	 8

Household Income	 8

Forestry	 9

Economic Impact	 9

Lessons Learned	 10

B.3		From Sector Development to Integrated Development	 11

B.4		Strategy, Government Input and Partnership	 12

Strategy and Government Input	 12

WFP and IFAD Partnership	 12

3.	Country Programme Evaluation	 14

A.	Overview and Context	 14

B.	CP Design and Strategy	 15

Basic Design Background	 15

CP Design	 16

Targeting	 16

Participatory Process	 17

Integration of Activities	 18

C.	Implementation of Basic Activities	 19

C.1		Investment in Human Capacity	 19

Design	 19

Achievement of Objectives	 19

Summary of Main Findings and Observations from Field Visits	 20

C.2		Land, Water and Natural Resources Components	 22

Design Issues and Relevance	 22

Summary of Main Findings and Observations from Field Visits	 23

Achievements in Guangxi and Gansu Provinces	 25

Mission Findings	 26

Work Norms	 28

C.3		Social Infrastructure	 30

Summary of Main Findings and Observations from Field Visits	 30

D.	Socio-economic Impact and Beneficiary Participation	 33

Beneficiaries	 33

Household Food Security and Self-reliance	 33

Poverty Reduction	 34

Livelihood Improvement	 34

Impact of WFP CP in the Context of China’s Economic Growth	 35

E.	Gender Aspects	 36

F.	Coordination and Partnerships	 39

G.	Resource Utilisation, Budget and Logistics	 40

Resourcing	 40

Counterpart Funding	 41

Logistics	 41

H.	Monitoring	 42

I.	Phasing out	 43

J.	Conclusions on CP Evaluation	 44

4.	Lessons Learned	 45

Tables

1.		Characteristics of a Sector Project and an IRD Project in Gansu Province	 11

2.		Contribution Planned by WFP, GOC and IFAD	 14

3.		Participants and Food Aid Beneficiaries by Activity Component	 15

4.		Average Food Aid Foreseen per Beneficiary Household	 15

5.		Total IRD Component (WFP Assistance) 2001-2005 per Activity as of May 2005	 19

6.		Outputs from Standardised Project Reporting	 22

7.		Outputs from Standardised Project Report (2001-2004)	 30

8.		Examples of Average Food Rations Supported by WFP in Visited Villages	 33

9.	Example of Food Support Received by Household Spread over Years	 33

10.	Increase in Yields through Land Improvement	 34

11.	Changes in Average Income per Capita (2002-2004)	 34

12.	Impact of Human Capacity and Social Infrastructure in Villages Visited	 35

13.	GOC Inputs 2001-2005	 41

Annexes

Annex 1	-	Terms of Reference for the Evaluation of WFP Operations in China

Annex 2	-	Allocation of Resources (1979-2005)

Annex 3	-	WFP Projects per Sector/Activity (1979-2001)

Annex 4	-	WFP Food Allocation per Sector/Activity (1979-2005)

Annex 5	-	WFP Projects Profiles with Activities and Food Utilisation (1979-2005)

Annex 6	-	Chart - From Sector Interventions to Integrated Rural Development

Annex 7	-	Map - WFP Resources per Province (1979–2005)

Executive Summary

(i)	WFP’s involvement in China started in 1979 and, to date, some 4 million tons of food worth a total cost of about US$1 billion have been delivered through 67 projects and one Country Programme. The Government of China contributed US$1.16 billion as counterpart funds while IFAD, starting in 1996, has been associated and consented loans for a total amount of US$148 million through 6 joint projects. Over the period, it has been estimated that close to 30 million people have benefited from WFP assistance.

## (ii)	Food aid has played a critical catalytic role – with financial and technical inputs - in enhancing the development process of poor households. Socio-economic indicators indicate a dramatic improvement in the living conditions of the beneficiaries. Results are exceptional with regard to physical achievements, mobilization of beneficiaries, efficiency in food management and sustained support from the Government. Coordinated Government action is a major ingredient to a successful integrated approach to poverty alleviation. The Project Management Office structure has clearly demonstrated a successful integration of different Government ministries for the implementation of multi-sectoral development projects and could be a model for other countries.

## (iii)	Cooperation between different UN agencies, and especially between the three Rome-based agencies, resulted in successful programmes. The joint preparation and implementation of IFAD and WFP-assisted projects has created a synergy in combining the complementary capacities of the two organisations especially in the field of education, training, health and income generating activities. Significant technical assistance provided by FAO, mobilized directly by WFP or through a UNDP “Umbrella Project”, has contributed to the sustainability of the WFP-assisted projects in China. However, the relative decrease of in-depth project formulation, systematic organization of technical reviews and evaluation missions during the last decade has indeed hampered project implementation, necessary adjustments and corporate learning.

(iv)	Adjustments have been made to address specifically women in development. Today, women represent about 57 percent of the participants for Food-for-Training and 50 percent for Food-for-Work activities. CP activities have helped to shorten the food gap and to some extent alleviate women’s traditional workload (water, straw or wood fetching and grain processing) and create new opportunities for income generation activities for women, although this has in some cases increased the women’s workload.

(v)	The current Country Programme (CP) has showed a gradual and substantial increase of the Chinese Government’s cost share including the costs of ocean freight and all landside transport. The combination of investments in productive infrastructure, training, social infrastructure and micro-credit brought commendable results. However, limited WFP resources - due in particular to food shortfalls experienced in 2003 and 2004 - were distributed in a too large number of villages. When limited resources are spread out, households do not benefit from the synergy between project activities. The overall impact has consequently been diluted. Furthermore, the programme approach has resulted in weaker technical appraisal and monitoring of basic activities.

(vi)	The results achieved by the CP constitute a clear illustration of the positive findings of the recent evaluation of the WFP “Enabling Development” policy (EDP) especially regarding (a) the benefits derived from increased agricultural production, basic social facilities and income-generating activities; (b) the selection of activities targeted on the poorest populations who have marginal assets and live in remote and under-serviced areas; (c) the existence of solid partnership especially with the Government; (d) progress made with respect to enhanced inclusion of women in the benefits of WFP development activities. On the other hand, the limited performance of WFP in demonstrating results and in monitoring and analysing efficiency-related issues as well as the resource-limitation-related problems pointed out by the EDP evaluation are also quite present in the China CP.

(vii)	The phasing out of WFP assistance has prompted early WFP Programme Officers’ departures and systematic monitoring has become sporadic, reducing WFP’s ability to follow the implementation and impact of activities. At the phasing out stage, it is recommended that particular attention be paid to a proper level of resources – both in commodities and in staffing – to ensure sustainability and to capitalize on the experience gained.

# Introduction

Purpose and Scope of the Evaluation

## The main objectives of the evaluation were to: (i) review and record the main elements of WFP’s 26 years of assistance to China in a succinct manner; (ii) evaluate WFP’s current Country Programme (CP), with a focus on activity outputs and impact; and (iii) capture lessons which may be of wider corporate interest, as part of WFP’s broader learning initiative. The main entry points for the evaluation of the on-going CP (2001-2005) were: (i) the consistency with WFP’s core mandate, the Enabling Development policy and the Enhanced Commitments to Women; (ii) design and achievement of objectives; (iii) targeting and implementation; (iv) impact and sustainability; (v) monitoring and reporting; (vi) coordination, partnerships and beneficiary participation; and (vii) budget and resources.

Methodology

## An historical review of WFP’s assistance to China was undertaken based on approved project documents, progress reports, completion reports, technical review reports and evaluation reports.  This desk study was undertaken in Rome, prior to the evaluation mission’s travel to China. The review has provided the required statistical data and background setting for the subsequent field work and evaluation.

## The evaluation mission visited China from 9 to 28 May 2005. Most of the mission’s time was devoted to the Country Programme evaluation. The mission was fielded in two provinces, namely Guangxi Zhuang Autonomous Region, where WFP 3730 “Integrated Agricultural Development Project in the Mountainous Area of Shanglin, Mashan and Xiangzhou Counties” was completed in 1997 and an on-going 9997/IFAD 552 is still operational, and Gansu Province in Loss Plateau with a completed WFP 3355 “Agricultural Development Project Through Irrigation in Jingtaichuan Command Area” and on-going WFP/IFAD Rural Integrated Development Project. They are major interventions under CP in terms of WFP’s contribution. Interviews were conducted with beneficiaries of WFP assistance and participatory evaluation sessions were undertaken with Project Management Offices (PMO) staff.

## This report encompasses the historical review (1979-2000) and assessment of WFP’s 26 years in China (Section 2), presents an evaluation of the current CP implementation (Section 3) and, ultimately, draws lessons of a corporate nature to be considered for a proper implementation of WFP-assisted development or rehabilitation operations in the rural sector (Section 4).

## Review and Assessment of WFP’S 21 Years in China

A.	Evolution of WFP’s Assistance to China (1979-2000)

## An historical review starting in 1979 was undertaken based on data from project documents, project completion reports and evaluation reports. WFP’s Executive Board has approved 67 WFP-assisted projects and one CP, providing some 4 million tons of food, worth about US$1 billion (see detailed allocation of resources in Annex 2). The Government of China (GOC) contributed US$1.16 billion as counterpart funds while IFAD, starting in 1996, provided loans for a total amount of US$169 million. Over the period, it has been estimated that close to 30 million people benefited from WFP assistance.

## WFP’s assistance to China can be presented in four main phases:

- 1979-82: Emergency food assistance to refugees and people affected by natural disasters. WFP assistance to China started in 1979 with the provision of emergency food assistance to Indo-Chinese refugees in the provinces of Guangdong and Yunnan through a series of Quick Action Projects.

- 1983-1990: Sector development strategy (forestry, fishery, agriculture and dairy projects). During this period the agricultural sector of China was undergoing significant changes following the establishment of the Household Responsibility System. Agricultural productivity and total production were given high priority by the Government and showed remarkable growth rates. WFP was associated with this policy through the implementation of large sectoral projects. The peak of WFP assistance was reached during that period (see Annex 2).

- 1991-1996: Integrated Agricultural Development (IAD) strategy aiming at securing a better production base in government selected townships with spot improvements of water supply systems and soil conservation works through Food-for-Work (FFW) activities together with ad hoc training. Project design was focused on technical features rather than on promoting and expanding farmer's participation during design and implementation. Existing mechanisms of farmer organizations were considered sufficient.

- 1997-2000 - Integrated Rural Development (IRD): In the mid-1990s, WFP began shifting its support from an IAD approach to an IRD approach which, in addition to meeting the food and income needs of the poor, also addresses human capital formation. The increasing recognition by the Government that achieving a more effective and sustainable poverty reduction requires integrated services, led to the decision in 1996 by the Ministry of Agriculture, WFP and IFAD to establish a programme partnership.

## Over the 26 years of WFP’s intervention in China various improvements were made regarding: (i) better targeting of poverty stricken areas and fine tuning of activities to try and address specific target groups; (ii) introduction of participatory planning; and (iii) recognition by the Government that a poverty reduction will require other development opportunities for the rural poor, such as access to micro-finance facilities and a better access to various social services and setting up social safety nets for the poorest.

## The following areas to be improved were identified during the preparation of the on-going CP: (i) the need for better training packages and improving agricultural extension approaches; (ii) better implementation and coordination of the micro-credit activities, both in timing, in overlap of activities between WFP and IFAD and ensuring that income-generating activities get promoted beyond standard agricultural or livestock loans; (iii) more and improved gender focus has been achieved, women’s involvement still needs to be improved; (iv) participatory design and continued involvement with the beneficiaries during implementation have to be strengthened ; (v) more attention to smaller scale infrastructure activities, in order to be able to meet community requirements, and if only bigger infrastructures are planned more attention needs to be invested in designing the tail-end elements of these infrastructures with those farmer groups who will take over their future maintenance; (vi) farmer associative groups need to be promoted during project implementation and appropriate guidance and training developed; (vii) a more flexible implementation system taking full advantage of a joint Annual Work Plan and Budget (AWPB) system and regular amendments to plans according to field implementation; (viii) better timing of food to beneficiaries needs to be checked in future projects to ensure that the targeted households receive a sufficient food package through the various activities they are concerned with; and (ix) the need to continue to provide the linkages and opportunities for the PMO to additional know how from within or outside China.

B.	Conclusions on WFP’S Assistance to China (1979–2000)

### B.1	Overall Assessment

##### Use and Role of Food Aid

## The food input from WFP has been mainly wheat. It has been delivered in bulk to the port nearest the project area, where it was either absorbed into government stocks with an equal quantity of similar quality wheat or equivalent amount of wheat flour or rice being made available to the various grain stations located in the project areas, or transported by rail from the port to the railhead nearest the project and then trucked to the project area grain stores. Beneficiaries received one family ration of 3.25 kg of wheat for each day of work as defined by established work norms for each type of activity.

## WFP food aid has contributed to meeting the short-term food consumption needs of poor, food-insecure households, while creating assets to make a shift towards more sustainable livelihoods through improving the areas and provided ad hoc training. The role of food aid has been an incentive to the beneficiaries to participate in project activities, to diversify agricultural production and to develop sideline activities. WFP food assistance has also served as a budgetary support to the Government which made savings in as much as it no longer had to provide relief and “resold” grain to these food insecure and vulnerable areas. WFP negotiated that these government savings be invested in the same project areas to build social infrastructures to improve education, health and sanitary conditions.

## Food aid has played a major catalytic role – with financial and technical inputs - in enhancing the development process. In addition, WFP’s approach and projects have also played a demonstration role for other programmes with and without food aid such as, for example, the on-going Land Conversion Programme, and the World Bank-funded North China Loess Plateau programme, Anshun Prefecture in Guizhou Province, which used its own resources to extend WFP project activities.

##### Physical Achievements

## The WFP experience in China is exceptional with regard to physical achievements, mobilization of beneficiaries, efficiency in food management and sustained support from the Government. All evaluation reports have highlighted outstanding physical and socio-economic achievements and stated that the objectives of the projects of raising food production, improving infrastructure, and relieving poverty have largely been achieved. Socio-economic indicators have indicated dramatic improvement in the living conditions of the beneficiaries.

## WFP-assisted project achievements in China have been possible however because of the overall context of the country’s on-going socio-economic transformations and economic growth. Projects have benefited from and contributed to these changes. WFP development interventions began in the early 80s, when the economic and agricultural reforms were initiated, triggering a tremendous increase in agricultural production, together with a spectacular annual growth of farmers’ income averaging 15 percent from 1978 to 1984, and still continuing though at a slower pace (2.1 percent in 2000). The composition of farmers’ income changed drastically with the growing importance of off-farm activities supported by industrial and construction sectors continuously in need of labour force.

##### Impact on Household Food Security

## To illustrate the impact of WFP’s intervention on household food security, it is meaningful to portray a typical project implemented in the Loess Plateau in the 1990s where a large part of WFP assistance has been delivered (see Map 1). Depending on locations and period of intervention, emphasis has either been placed on developing and protecting important irrigation command areas through infrastructure works, up-watershed afforestation, turning rainfed slope lands into irrigated terraced fields, or developing a wider pallet of smaller activities within a same catchment area combining dryland farming on terraces, afforestation, small irrigation facilities in the lowlands, and water harvesting at farm level. Complementary productive oriented activities such as economic forestry and/or livestock activities within the same area, access to seasonal farming input packages, and improvement of access roads were usually also undertaken.

## Land improvement assisted works have induced increased yields and achievement of self-sufficiency. Before WFP intervention, the arable land of an average household with four persons amounted to 0.75 ha of slope land and 0.17 ha of terraced land. Grain production was about 1 mt per household, which left a food gap of approximately 2 to 3 months a year. Thanks to project activities (notably turning slope land into terraces) the total household grain production reached 1.3 to 1.4 mt, covering the household’s basic requirements.

## The evolution of farm and family incomes has shown a steady increase. At full development, the total net family income, in constant value term, is globally twice the income registered before project implementation. Composition of household income has also changed. Revenues from animal husbandry activities increased from 10 to 30 percent of agricultural production, mainly due to the use of grain surpluses to feed pigs. Whereas before the project agriculture was the main source of household income (over 75 percent versus 25 percent for sidelines activities), after the project, off-farm employment represented at least 50 percent of the household’s income. The part of income drawn from cash crops and fruit production (project plantations) increased as well. The Economic Internal Rate of Return (EIRR) calculated at project level - during the sectoral evaluation of rainfed agriculture in the Loess Plateau - was established at 17 percent (to be compared to the cost of capital of 12 percent at that time in China).

##### Sustainability

## The increased involvement of beneficiaries in the design and monitoring of projects through Participatory Rural Appraisal (PRA) exercises has contributed to increase sustainability. The construction of social infrastructure including roads, domestic water storage and health centres, which already started in the mid 1990s and became the central focus of CP activities, contributed to improve the overall sustainability, alleviating the daily workload especially of women.

## Upgrading, maintenance and operation of major irrigation schemes require important investments, which are borne at present by the Government and not fully reflected in production costs at farm level. In addition, main buildings and inter-farm canals, which are under the responsibility of the Water Conservancy administration, are well maintained and operated, while on-farm canals were not included in the construction works and have not been completed, hampering the potential efficiency of the system. Training played a growing role in the WFP-assisted projects but its impact was at times diminished by teaching methods and content not always adapted to the education level, living conditions and farmer needs. Impact on the environment remains a challenge, experience showing that additional measures are always required to avoid subsequent environmental threats such as salinisation.

## Projects in the early 1990s were in general primarily centred on productive infrastructure development, and long-term impact at household level was not the main priority. For example, areas planted with economic trees during this period were often under collective land use rights and were contracted to entrepreneurs (long-term benefits for the household being limited to the low rent paid to the village and utilised for social welfare). Within the IRD projects, focus was deliberately put on household development, resulting in actual appropriation of assets by the beneficiaries.

### B.2	Sectoral Development

##### Overview

## In the beginning of the nineties WFP’s evaluation service commissioned 4 evaluations to learn about WFP’s contribution to the results and impact achieved in 4 sectors supported by WFP: (i) Hydro-agricultural activities (irrigation and drainage); (ii) Rainfed Agriculture (Dryland improvement and development); (iii) Forestry; and (iv) Fisheries. The overall findings from the evaluations were that the WFP-supported projects had achieved their targets and objectives. The quality of the works performed with the help of WFP food aid were generally found to be of good quality, and to have contributed considerably to the improvement of the living conditions of the beneficiaries. The projects were found to have benefited from well established local institutions and readily available government facilities for transport, storage and distribution of WFP food commodities. The evaluations established that China was well set up to store and allocate food, as the Government had long been a distributor of subsidized grains. The management of WFP food was found to be satisfactory and the effectiveness of the distribution was described as the result of good coordination between the key institutions involved.

## The projects have usually been planned and managed by local government entities. The evaluations found that the Chinese government generally gave considerable priority to them at all administrative levels. The projects were found to be consistent with the long-term government policies on increasing production of food and industrial crops, to raise the income of the rural population and to create non-farm employment opportunities in rural areas. The evaluations concluded that WFP’s food aid has had following role in this context:

- budgetary support to the central and provincial governments that contributed to the undertaking of works, which could not otherwise have been carried out, or would have been delayed due to lack of funds;

- enabling Government to make savings on relief and resold grain provided to the projects;

- an incentive to the beneficiaries to participate and thereby accelerate the land improvement;

- attraction of skilled workers from outside the project area when the local labour force was insufficient;

- a subsidy to families that contributed to the coverage of the food gap, and encouraged to diversify production and develop sideline activities such as pig and poultry production; and

- as compensation for low yielding agricultural land in case of conversion into forest, pasture, etc. for protection.

##### Irrigation and Drainage

## WFP assistance to China for the establishment of hydro-agricultural development works, provided between 1981 and 1992, accounted for approximately 21 percent of total WFP assistance for that period and was made available through 25 projects. Most of the assistance was through FFW initiatives to rehabilitate and develop existing irrigation infrastructure to increase food production and thereby the income of the rural population. In addition some road construction, forestry establishment and rural water supply have been developed.

## In 1991 WFP’s evaluation service undertook an evaluation of WFP’s assistance to the hydro-agricultural sector since 1981. It was based on desk reviews and in-depth assessments of 6 projects considered representative of the various conditions under which the projects were implemented. The overall conclusion of the evaluation was that, based on the information from the project authorities, the targets established for the outputs appear to have been achieved or exceeded. Through visits to the 6 selected sites the mission observed that the construction quality of WFP-assisted works were generally good. Among the specific technical problems identified were incorrect land levelling affecting the fertility of the land and inadequate design of cross drainage of the mountain side canals posing a risk to the stability of the canals themselves, and dam safety measures and a lack of sediment traps in the pumping schemes in Gansu. Problems related to the maintenance of a favourable salt balance were seen in Gansu and eastern Quinhai. According to an analysis carried out by OEDE in April 2005, a total amount of 400,000 hectares were brought under irrigation during this period.

#### Economic Impact

## In terms of increasing food production and income of the rural population, analysis of data from before and after the implementation of the projects show significant increase of grain production per capita and household income. In Gansu and Quinghai, yields of wheat (main staple cereal) have increased form below 0.9 mt per ha to 4.5 mt per hectare. In the southern provinces where rainfall is higher, the provision of irrigation to the project areas has resulted in an increase in the rice yield from less than 1.88 mt per hectare to 4.13 mt per hectare.

## In the least favourable cases grain production per capita increased from 139 to 300 kg representing an increase of 161 kg or 116 percent over the situation without the project. This is the case for project 2708, where people were already practising irrigation, and where only 46 percent of cropped land is irrigated. For projects 2639 an 2697, where beneficiaries are settlers from arid land, and crop land is fully irrigated, grain production per capita rose more dramatically. At full development the net per capita incremental value of agricultural production ranges from RMB 220 for farmers in project 2708 to about RMB 380 in Project 2719. Cropping intensity also increased. In Guizhou irrigation has allowed double cropping and in Hainan Province up to 3 crops a year can now be grown in the better areas of the WFP-assisted schemes.

## The increase in grain production represents an important improvement of the income position of participants. With projects, the income range from RMB 4.8 a workday to about RMB 10, compared to approximately RMB 2 per workday without the projects. When interviewed, the farmers reported that they used the additional income to improve their houses including sanitation facilities, clothing as well as for productive reinvestment in agriculture.

## The evaluations observed that the projects had contributed to improvement in the living conditions of the beneficiaries evidenced by increased accessibility to services such as drinking water, schools and health facilities, and housing improvements.

#### Sustainability

## The evaluation found three main positive indicators concerning sustainability:

- the Project Management Unit that implemented projects have been adjusted and institutionalized as permanent government bodies for pursuing the purpose of the projects after the termination of WFP assistance;

- despite delays recorded on a few occasions the provision of government funds has been generally satisfactory; and

- an important part of maintenance activities is carried out by household groups through a contract system.

##### Rainfed Agriculture

## WFP assistance to China for rainfed agriculture provided between 1981 and 1992 accounted for approximately 13 percent of total WFP assistance to China, and was made available through 9 projects. Most of the assistance was through FFW initiatives to eliminate erosion by constructing terraces and/or planting permanent vegetation. The purpose was to ensure a higher grain production per ha and enable the conversion of marginal cropland into fruit tree, fodder and forest. Road construction was developed to improve access to the project areas.

## In 1992 an evaluation of WFP’s assistance to the sector was undertook. With regard to rainfed agriculture, activities in the Loess Plateau were considered to be the most representative of WFP assistance. It was therefore decided to draw conclusions on the results and impact of the assistance to this sector based on an in-depth evaluation of two projects in the Loess Plateau, namely 2744 “improved land use of the Loess Plateau, Mizhi County, Shaanxi Province”, and 3225 “integrated Development of the Xingzihe watershed, Yan’an Prefecture, Shanxi province”.

#### Erosion Control

## The overall conclusion of the evaluation was that the projects had met their targets for physical outputs and achieved the objective of reducing erosion and soil loss while increasing the income of the target beneficiaries. According to an analysis carried out by OEDE in April 2005 approximately 82,000 hectares were terraced during the period under review. Most of the works were found to be adequate and of good quality, with the exception of a few cases of landslides in terraces possibly caused by exaggerated dimensions and weak mechanical maintenance. Some of the older terraces needed restoration and water logging, salinization and siltation problems already noticed in former missions had remained unattended. According to information from the PMOs, the most immediate effect of the works has been a substantial reduction of soil loss within the water catchments covered by the WFP projects. Compared to soil loss before the projects started measured in ton/km/year, a 83 percent reduction in soil loss was achieved in Project 2744,  and 62 percent in 3225 (at the time of the evaluation, 3225 was still on-going). Data available did not indicate the extent to which the projects have contributed towards an overall sediment rate reduction in downstream networks and watersheds. However, some official reports claim that a general soil loss reduction of about 50 percent in the Wuding–Huanghe confluence area was achieved.

#### Impact on Household Income

## The WFP-assisted projects have contributed towards a steady rise in income of beneficiary household. The total net family income in constant value terms registered by the evaluation was twice the income registered before project implementation. The structure of the incremental value, however, showed that the share coming from food and cash crops was minimal. Yield increases, resulting from turning slope land into terraces, have been basically counterbalanced by the reduction of land for food crops available per household. Revenue from livestock raising had notably increased, but it originated from sideline activities like pig and poultry, although it had been foreseen that pasture improvement would have led to a larger income from sheep and goats. At the time of the evaluation the fruit trees and orchards were too new to show important yields, but the evaluation was foreseeing that the income would become an important source in the future. The fact that the major change in revenue comes from the sideline activities is an indication that whereas employment had been stimulated by revenue increases, household revenue form agriculture had perhaps reached a limit, and thus farmers were looking primarily towards off-farm income. In some cases household participation in FFW activities reached as many as 300 working days per year per family. This could possibly have diverted labour from farming activities, thus the importance to identify labour availability during project design.

## As a result of the income increase most of the farmers interviewed no longer held loans from the Agricultural Bank of China as they did before the projects started. Instead they were found to have savings which often amounted to the annual net family income. All socio-economic indicators concerning health, housing, farm equipment, indicated that these had been a considerable improvement in living conditions. However, despite efforts to increase the number of safe drinking water wells in particular, water collection for human use continued to be a burden for many villages. Access problems limited the possibility for export of the agricultural produce and the evaluation found that 22 percent of the villages in the project areas that were visited were not accessible by road.

##### Fisheries

## WFP assistance to the Chinese fishery sector, provided between 1982 and 1988 accounted for approximately 11 percent of total WFP assistance to China, and was made available through 6 projects. The total value was US$110 million. Most of the assistance was through FFW initiatives to build hatcheries, feed mills, cold storage, etc. and to put into production some 6,000 ha of fish ponds for aquaculture on waste or low productivity land in order to eliminate pockets of poverty within the counties of implementation. Two of the projects were directed primarily at fishermen and were intended partly to reduce fishing pressure on declining lake or marine fish stocks. One project included activities to improve the fish stocks in a lake that had become over-fished, and to resettle families living on boats on the lake, providing them with houses schools and hospitals. In each project some relevant infrastructure was provided for the project area including roads, bridges, pumping stations electricity transmission lines and office buildings.

## In 1989 WFP’s evaluation service undertook an evaluation of WFP’s assistance to the fishery sector. It was based on desk reviews and in-depth assessments of 4 projects. The overall conclusion of the evaluation was that WFP’s assistance has contributed to more effective utilization of waste or low-productivity land, created considerable short-term and long-term employment, increased availability of animal protein on a sustained basis, and has helped to improve the social and economic opportunities of target populations. Through visits to the four selected sites the mission observed that the construction quality of WFP-assisted works were generally good. In the WFP project areas ponds have generally been made somewhat deeper and in addition to supplemental fertilizers and grasses some pellet feeds were also added. This allows for higher proportions of the more expensive species (grass carps and common carps) to be raised, as well as increasing the overall production. The average production from WFP ponds was said to be about 2.5 tons per hectare, compared to a national average of 1.64 tons per hectare outside the project areas. Based on these average production figures, the total annual production from the projects evaluated was about 21,000 tons of fish. Compared to the annual fish production in China in 1987 of 9.5 million tons, those projects contributed about 0.8 percent of output from fish pond culture in the country and about 0.2 percent of total fish production. On an annual 10 kg per capita basis these projects supply the annual domestic fish intake for about two million Chinese people.

#### Household Income

## The income of fishermen in the project areas reportedly went up significantly in absolute terms. In the Hongze Lake areas the annual per-capita income of fishing families increased with between 17 percent and 56 percent annually and continued to do so after the projects had ended. In Project No. 2730 per-capita income for project participants increased from about RMB 69 in 1982 to RMB 180 in 1987. While income has been declining significantly among those in the Project No. 2771 area (from 200 dollars in 1977 to 88 dollars in 1982) by the completion of the project, this decline had not only been turned around, but income had gone up significantly each year. The evaluation team concluded that this suggested a reasonable degree of sustainability. Income distribution among pond operators varies considerably. The mission observed very prosperous fish farmers participating in the work schemes. In these cases the average size of the group was then increased so as to spread the benefits of the same size pond more widely.

## The key differences between these WFP-assisted projects and other development initiatives, throughout the rural areas of the project provinces, lie in the level of concentration of investment in the local area, the degree of government control over the resulting infrastructure and the degree of indebtedness created. WFP assistance does not have to be repaid and has provided investment capital to allow earthworks and construction work for productive facilities to start up earlier and to proceed more quickly than would have other wise been the case.

##### Forestry

## WFP assistance to the forestry sector between 1981 and 1992 accounted for approximately 12 percent of total WFP assistance to China, and was made available through 8 projects for a total value of US$138 million. In addition forest plantation has been included in 14 agricultural projects usually for protection in the form of erosion control or wind belts. In total forestry activities make up 21.6 percent of total assistance between 1981 and 1993. Most of the assistance was through FFW initiatives to plant trees for protection of agricultural land and/or for economic purposes like animal fodder, timber, fuelwood and fruit trees to improve living conditions for rural poor populations.

## In 1990 an evaluation of WFP’s assistance to the sector was carried out. The evaluation team undertook a desk review of 22 projects and visited 4 projects in 4 provinces. The overall findings were that the assistance to the forestry sector was appropriate, generally of good quality, and that the projects had met their targets for physical outputs. It was estimated that by 1990 with WFP assistance more than 146,000 hectares had been afforested, some 74,000 of denuded or marginal land had been put under fodder cultivation and 16,000 hectares of Camellia Oleifera had been regenerated for oil production. According to a calculation made by OEDE in April 2005, 360,000 hectares had been afforested. Survival has been very satisfactory compared to earlier projects in similar areas of China. However, the mission identified a few shortcomings in the institutional coordination, in the possibilities of readjustments of project objectives, in cost analysis, and in the plans for long-term sustainability of the assets created by the projects.

#### Economic Impact

## The forest works’ impact on preventing environmental degradation and protecting agricultural production is difficult to measure in monetary terms, but it has definitely been important. The cost-benefit ratio from the plantations was at the time of the evaluation estimated to be between 3.1 and 4.6 to 1 over 20 and 10 years respectively. Under the household responsibility system farmers have the right to the management and to the personal accumulation of income generated from the sale of production minus a small part that goes to the collective. However, the mission observed that the rights and obligations of the farmers and the price indexation to be used regarding the produce sold to the Government was not always clearly spelt out in the project documents, which could jeopardize management and maintenance of the planted areas.

## The income transfer in form of food aid given to farmers as a compensation for giving up their low yielding farm land for forestry projects was an important contribution to the household economy. The grain availability per capita for the selected beneficiaries in Hunan before the projects was 200 kg. In the three project areas visited by the evaluation mission 96,000 out of a total of 147,000 households reportedly participated in the project (65 percent of the households) each receiving on average 674 kg of wheat and 11.7 kg of vegetable oil over a period of 5 years. During the project years the grain availability rose to 300 kg per capita creating average cumulative saving of 150 Yuan annually per household. The farmers reportedly spent these savings on increasing their standard of living through improvement of their housing, purchase of durable and non-durable consumer goods, and to acquire agricultural tools and fertilizers to increase farming productivity.

Lessons Learned

## All the sectoral evaluations gave specific recommendations on technical issues, many of which were followed up by the project management units. Hereafter are listed the cross sectoral lessons learned of corporate interest:

- Various factors external to the projects have contributed to their successful implementation: availability of markets, access to credit and non-food inputs, agricultural extension and high government commitment at all levels.

- The household responsibility system helped to ensure the quality of the works since the food rations are distributed only after inspection of the works (except for the lean season when food advances were given).

- Food aid assistance to agricultural development in general and irrigation in particular has proved to be an efficient and effective way of increasing production and household income and in mobilizing additional government investment in rural areas.

- A systematic organization of technical reviews and evaluations is needed during project implementation in order to adapt the operational plans to changing needs or new technical requirements that may emerge during implementation.

- Technical assistance and supervision is essential to the achievement of the desired results. More attention should be given to maintenance and access to technical knowledge.

- If farmers have no definite guarantee with regards to the land contract and to the future prices of the produce, the protection and management of the areas planted could be jeopardized.

- More attention should be paid to the financial and economic analysis as part of the design process. Sustainability indicators need to be considered from design and should be monitored.

- When more than two institutions are involved in the implementation, more attention needs to be paid to coordination to ensure adequate timing of the inputs and harmonized reporting requirements. For multi-sector projects it would improve the efficiency if WFP had only one responsible counterpart.

- Women have been recognized as equal partners with a very active participation in planting and cropping and maintenance activities. However, the number of women taking part in the training programmes remains low with regard to the important role they play in project implementation.

- Training programmes for project management staff have contributed towards a satisfactory technical implementation of project activities. Methodology of financial and economic analysis of the projects should be included. Training for farmers should be directed towards practical skills (e.g. fertilization and pruning of fruit trees, new techniques should be given particular attention).

B.3.	From Sector Development to Integrated Development

## The example of two WFP-assisted projects, one sector project and one IRD project, both carried out in Gansu Province, illustrates the approaches adopted through different periods of assistance and their respective impact on livelihoods and households’ economy.

## WFP-assisted projects have always been targeted to remote areas with poor environmental and socio-economic conditions. The IRD projects focus on the extremely poor (200 Yuan average annual per capita income), living in extremely remote mountainous areas, with little scope for improvement in agricultural production, 5 to 6 months annual food gap and poor sanitary conditions.

## Sector Development interventions (notably irrigation projects) concentrated on a specific area to be developed, where population from neighbouring poor villages was re-settled. Beneficiaries often started from scratch but benefited from the water resources of the Yellow River and the large flat land to be claimed and irrigated on the Loess plateau. Re-settlement was planned by Chinese authorities, and process was in place to control the number of migrants according to amount of land available. All settlers benefited from almost the same investment and activities. IRD projects were carried out in mountainous villages, were arable land is scarce, with little potential of land improvement through terracing, and where road construction and maintenance is expensive due to topographic and climatic conditions. The project proposed a variety of training and infrastructure activities, and each beneficiary household did not participate into the whole range of activities but to a few of them.

## The amount of food aid per beneficiary was significantly lower in the IRD project (US$21) than in the sector project (US$96). Large investments made for irrigation infrastructure resulted in an immediate increase of the grain output as a combined effect of arable land reclamation and increase and stabilisation of yields through irrigation, ensuring households food-security (grain production per capita increased up to 5 times). The impact of IRD project activities on agricultural production has been more modest and full food security could rarely be achieved.

## The IRD model has had a direct social impact on the beneficiaries through education and training. Its strength has been to address directly literacy (illiteracy rate decreased) and capacity building (half of the beneficiaries receive agricultural technical training), to target the poorest and especially women, whereas social impact from sector projects was expected indirectly through beneficiaries and government investment in construction of school and health facilities.

Table 1 - Characteristics of a Sector Project and an IRD Project in Gansu Province

### B.4	Strategy, Government Input and Partnership

##### Strategy and Government Input

## The conceptual approach and design of WFP-assisted projects has been adapted to better integrate poverty alleviation requirements. The IRD approach progressively introduced put particular emphasis on human capacity building and food for assets to the direct benefit of households. Evaluation reports of projects implemented since the mid-Nineties show that the blend of technical training programmes, literacy programmes, and women development centred measures initiated a real and positive change in the way farmers take part in project implementation. PRA methods used during planning and monitoring have helped to implement the IRD approach. However, the strategy adopted, especially during the CP implementation, to reach as many beneficiaries as possible, and combined with resource shortfalls in 2003 and 2004, has resulted in a large spread of resources diluting the impact of project activities.

## Strong government support in terms of financial resources and sound technical backstopping from Provincial and Township Technical Bureaux have always been forthcoming during project implementation. The structure of the PMOs put in place by the Government has proven to be very efficient for project implementation.

## WFP assistance has been closely linked to the government’s comprehensive development programmes. WFP-assisted development projects have been implemented in targeted poor, remote, and food-deficit areas with difficult access and prone-to-erosion environment. Beneficiaries were local farmers relying mostly on agriculture for their subsistence. WFP assistance, which represented typically 20 to 30 percent of the total investment of such programmes, played a crucial role in their timely and quick implementation and completion, hence helping the Government to reach its long-term objectives for rural development.

## The combination of investments in productive infrastructure, training, social infrastructure and micro-credit (through IFAD support) brought commendable results. Technical assistance provided by FAO for project appraisals, technical reviews and evaluation has proven to be very useful for efficient project implementation and sustainability.

##### WFP and IFAD Partnership

## The IFAD/WFP partnership started in 1996 to join forces with the Government to reduce poverty and hunger in remote rural areas. The partnership has enabled the successful integration of education, training, health and credit components into multi-sectoral activities, making a significant impact on the improvement of rural livelihood while reducing operational costs for both agencies and the Government. A major part of the IFAD loans has been used for the provision of credit to poor rural households, but the proportion of loan funds allocated to this activity has declined in recent IRD projects to better capture all the benefits of the synergy GOC-IFAD-WFP partnership. Nine of ten joint WFP/IFAD development projects have been fully or partially implemented. One has not yet been approved by IFAD Executive Board.

## Key features of IFAD-WFP partnership include a shared vision, joint project design, joint targeting through Vulnerability Analysis and Mapping (VAM) use and joint implementation. The common vision of the GOC-IFAD-WFP partnership is that graduation out of poverty is a step-by-step process. The first step is to meet the food gap through WFP FFW  for community social and economic infrastructure (road, water and sanitation, primary schools and health care facilities) and to enhance human capacity through functional literacy training; the second step is to ensure household food security through FFW for land improvement and related skills training in crop and livestock production; the third step is to raise incomes above the poverty line by introducing IFAD credit and related training for cash-generation activities. Local microfinance institutions like Rural Credit Cooperatives (RCCs) are supported to improve their capacity to deliver credit and services to the poorer segment of the rural population.

## The ideal synergy between IFAD and WFP has not always been reached for reasons elaborated in a report of WFP/IFAD Partnership in China. The main conclusions of this report are as follows:

- the synergy between IFAD/WFP components with regards to timing and geographical coverage needed to be improved. A misunderstanding on the part of the local government and PMOs led to spreading IFAD/WFP assistance in order to achieve larger coverage, despite the fact that the intention was to serve the same beneficiaries;

- targeting below township level needed improvement. The selection criteria were insufficiently transparent. Broad-based participation in Village Development Plan (VDP) formulation was yet to be achieved;

- joint supervision including staff TORs, WFP inputs, and FFW/FFT components; and

- M&E systems were too focused on output indicators (ha of irrigated land, ha terraced land, etc.) and not paying enough attention to the outcome level results such as the number of household that have increased their income. Village Implementing Groups (VIGs) were asked to categorize the households between very poor, poor and non-poor and create a household level database that can be aggregated upwards to county level.

## The evaluation team further recommended that the agreement between WFP and IFAD should be formalized with regards to shared principles for joint formulation, targeting, implementation, supervision, M&E and cost sharing. This recommendation was not followed in practice. During the on-going CP, uncoordinated IFAD/WFP interventions have resulted in joint programme with different project areas and different target groups. In Gansu, a number of 22,649 women have received training for income generation activities while IFAD loan is still yet to be approved. PMOs have recognized the problems and indicated that RCCs would replace, to the extent possible, IFAD loans. However, in the case of Gansu, it was clear enough from the beginning of the CP that IFAD loan was delayed. Local Government or other international organizations such as World Bank should have been approached to replace IFAD in that particular project. It seems that the problems related to synchronisation between the two agencies have been exacerbated since 2001 with the Ningxia/Shanxi Environment Conservation and Poverty Reduction Programme and the above-mentioned Gansu Agricultural Integrated Programme. IFAD project in Ningxia/Shanxi was started two years after the programme was approved and when WFP had almost finished its operation in this area.

## Full benefit of the IFAD/WFP partnership can only be obtained with a synchronized approach, where IFAD loans are distributed immediately after Food-for-Training (FFT) activities have been implemented as planned. Joint Government/IFAD/WFP mid-term reviews should have been systematically organized to reformulate some project components according to the availability of resources.

## Country Programme Evaluation

A.	Overview and Context

## 3.1	An exit strategy was discussed at WFP’s Executive Board at its Third Regular Session in 2000, whereby WFP assistance in China would be decreased over a five-year period, moving towards phasing out of WFP food assistance by December 2005. The on-going CP (2001-2005) was developed accordingly and approved in February 2001. The goal of the CP was to bring about sustainable improvements in food security for about 1.7 million poor households over the period concentrating its development activities on priorities 2, 3 and 5 of the Enabling Development Policy namely: (i) enable poor households to invest in human capital through education and training; (ii) make it possible for poor families to gain and preserve assets; (iii) enable households that depend on degraded natural resources for their food security to make a shift to more sustainable livelihoods.

## The multi-sectoral approach was chosen to address interrelated constraints through four basic activity components:

## Investment in Human Capacity;

## Land Development and Irrigation;

## Social Infrastructure; and

## Water and Soil Conservation.

## CP implementation has been organized, as in the past, through stand-alone projects. A supplementary activity of school feeding was foreseen subject to the availability of funds. Activities were to be implemented in ten provinces. Targeting was guided by Vulnerability Analysis and Mapping (VAM) techniques.

Table 2 - Contributions Planned by WFP, GOC and IFAD – (US$ million)

|  | WFP | GOC | IFAD | Total |
| --- | --- | --- | --- | --- |
| Basic Components: |  |  |  |  |
| Investment in human capacity | 13.6 | 24.4 | 22.2 | 60.2 |
| Land development and irrigation | 23.1 | 39.7 | 29.7 | 92.5 |
| Social infrastructure | 10.6 | 20.3 | 14.8 | 45.7 |
| Water and soil conservation | 8.6 | 15.6 | 7.4 | 31.6 |
| Micro credit |  |  | 74.1 | 74.1 |
| Supplementary Activity: |  |  |  |  |
| School Feeding | 30 | 109.6 |  | 139.6 |
| Total | 85.9 | 209.8 | 148.2 | 443.9 |

Table 3 - Participants and Food Aid Beneficiaries by Activity Component

|  | Programme Participants | Food Aid Beneficiaries | Female Participants No. | % |
| --- | --- | --- | --- | --- |
| Basic IRD Activity Components |  |  |  |  |
| Investment in human capacity (Food-for-Training) | 1,181,100 | 4,724,400 | 944,880 | 60 |
| Land development and irrigation (Food-for-Assets) | 620,000 | 2,480,000 | 310,000 | 50 |
| Social Infrastructure (Food-for-Assets) | 316,900 | 1,267,600 | 158,450 | 50 |
| Water and soil conservation (Food-for-Assets) | 244,200 | 976,800 | 122,100 | 50 |
| Total IRD | 2,362,200 | 4,724,400 | 1,535,430 | 65 |
| Supplementary activity – School Feeding | 500,000 | 500,000 | 350,000 | 70 |
| Total IRD and School Feeding | 2,862,200 | 5,224,400 | 1,885,430 | 66 |

- CP Design and Strategy

### Basic Design Background

## The concept of a multi-sectoral approach, where land development and irrigation measures would be combined with education, training, health and sanitation measures, constituted the basic foundation of the CP. The underlying idea was that single-sector approaches were not anymore effective in assisting the poorest in China. This referred specifically to the previous WFP-assisted sector-related projects. The CSO indicated that emphasis should be put on investment in agricultural infrastructure (land development and irrigation) to the benefit of human capacity building and social infrastructure.

## In line with the Enabling Development Policy (EDP), WFP's intervention was to be geared towards trying to cover the food gap experienced by the target benefiting households. “The focus of WFP food aid is on people’s priorities and livelihoods rather than on infrastructure development for temporary employment creation with food now considered essentially as a temporary support to people whilst their livelihoods improve, rather than as a form of payment”. The role of “food aid was to address the immediate consumption needs of the hungry poor”. In the CP, this gap has been estimated to be on average 3 months. This was to be provided to the same households over different years according to the local agricultural calendar and cropping practices.

## WFP food aid for the total duration of the programme was meant to cover approximately 75 percent of the food gap. For the duration of the programme, the total food aid foreseen, including the government contribution, amounts for 390 kg per household. This covers about 5 months food gap for a 4-persons household spread on the 3 to 5 years of the projects, which seems rather limited compared to the needs identified in the targeted poorest counties in China, where the annual food gap is currently up to 4 to 6 months. The average food aid per household has been further reduced later on during the planning phase (see Chapter “Implementation of CP Basic Activities”) to cover the large number of beneficiaries counties identified and to accommodate shortfalls in contributions in 2003 and 2004.

Table 4 - Average Food Aid Foreseen per Beneficiary Household

|  | kg | Days | % |
| --- | --- | --- | --- |
| Average food aid per beneficiary household | 387 | 119 | 100 |
| of which WFP food aid | 293 | 90 | 76 |
| Average food for training per beneficiary household | 94.5 | 29 | 24 |
| Average food-for-work per beneficiary household | 292.5 | 90 | 76 |
| Source: Country Programme China (2001-2005), WFP/EB.1/2001/8/1. |

## The programme approach adopted by WFP moved away from individual projects and "WFP will limit its development activities to those objectives which will be selected and combined in Country Programmes in accordance with the specific circumstances and national strategy of the recipient Country". This programme approach is more objective oriented and activities need to be implemented in line with these objectives. However, WFP's programmes more often than not consist in "Programmes, approved by WFP Executive Board, consist of a number of specific Projects, called Activities, within a Country for a set period, normally five years, to achieve a common goal". Whereas in the previous project approach each project was submitted to some form of appraisal and was to include its own monitoring and evaluation, the programme approach has simplified “project or activity” preparation and monitoring to one single overall appraisal conducted before EB's approval of the programme.

### CP Design

## The design of the China's CP was based on the work done with the Country Office (CO) and the MOA during the preparation of the country's CSO and is in line with EDP and standard programme designing. It is however heavily based on the assumption that the IFAD-WFP partnership was to be the backbone, enabling WFP to consider that the appraisal work conducted through IFAD according to its own procedures could be used as a shared baseline within which WFP could insert and define its own contribution.

## The CP has this particularity that it is more like a compilation of provincial programmes, called projects. Considering all projects as part of one overall CP has resulted in erasing or hiding the variety of situations and realities in WFP-assisted operations. It has also contributed to a much looser technical appraisal on each individual project and a looser monitoring and evaluation system (geared mainly to recording food distribution and number of beneficiaries).

## The Programme design being less site specific or sector specific has had the consequence that previous design and planning of activities has been translated into a list of individual assets and activities and that the more integrated geographical or watershed approach has been lost.

## The tripartite intervention should have required a specific mechanism to co-pilot the programme and be able to take the necessary actions to ensure timely delivery of all inputs from all three partners, common reporting and monitoring of a global project-programme log-frame.

## Constraints linked to the phasing out process (see Monitoring and Phasing out Chapter) have limited the CO’s capacity to analyse the M&E reports submitted to them by the PMOs, specially in 2005. No specific actions seem to have been taken to collect impact indicators in partnership with both other partners.

## The negative effects of these CP design features can be summed up as: (i) quality of activity documentation has declined with the lack of in-depth appraisals; (ii) identification of the minimum co-funding required to ensure to a WFP intervention a tangible impact; (iii) dispersion of activities to give each poor household an 'asset' has undermined the overall objective to provide improved livelihoods  “sustainable assets”; and (iv) no integrated follow-up and piloting of project-programmes that involved three different partners (GOC, IFAD and WFP).

### Targeting

## Selection of intervention areas has been achieved through the use of the VAM tool developed by WFP in China since 1997. Vulnerability was defined as the combination of exposure to risks and the inability to cope with them. The objective of targeting is to allow WFP to concentrate food aid resources on the most vulnerable people in the most vulnerable households in the least food-secure areas of the country.  Targeting was a two-step process: geographic and beneficiary targeting. The first was done by VAM through principal component analysis supported jointly by WFP and IFAD. The second was done by WFP and GOC, using primarily PRA techniques. A GTZ consultant helped to set up village targeting methodology and database, and provided training to PMO staff as well as County and Township staff.

## After completion of the CSO, an updated analysis and mapping was made in October 2000. In 2003 a new analysis was performed and the evolution is shown hereafter. Its major conclusions were that half of the vulnerable counties have remained the same (271), that most of the newly included vulnerable counties (71) were located on the Tibetan-Qinghai plateau and that over 171 counties, scattered throughout the country had sufficiently progressed not to be considered vulnerable in 2003.

## The analysis showed that about 70 percent of the vulnerable counties identified in this analysis match with the government priority counties for poverty alleviation. The difference between the two lists is understandable, because WFP identifies the vulnerable counties in terms of food insecurity risks, while the GOC list is based on the poverty situation of a county, which is often measured by income.

## The CP had foreseen that a final WFP supported provincial project was to be considered in Xinjiang, based on the VAM mapping of October 2000. However, based on the observations of the June 2003 VAM analysis and the shortfall in contribution, it was decided not to design a last project in Xinjiang.

## Regarding the projects visited by the evaluation mission, secondary township selection was carried out using similar screening procedures as those used in the October 2000 and June 2003. In both provinces a list of most vulnerable counties to be further screened was agreed on, before the WFP-IFAD China VAM unit proceeded with fine screening and clustering of townships within them. These lists of vulnerable counties have been in both cases a compromise between the WFP-IFAD VAM mapping, the list of poor counties as established by the Government and consideration such as avoiding overlap with other major donor projects.

## Targeting has thus been essentially done based on VAM screening of townships. It is not clear how the various administrative villages were selected at township level. At village level, selection of households seems to have been carried out through the VIG and during VDP preparation. In Guangxi extensive household surveys have been carried out to identify and group households in four different groups (rated A to D) and to focus interventions on households in Groups B and C. In Gansu, this seems to have been done through a kind of wealth ranking done at village level during preparation of the VDPs.

## There have been no other screening criteria used than those based on those developed by the VAM. Additional criteria such as concentrating in limited geographical areas, limited availability of project management capacity, existence (or capacity) of market opportunities to pull the general development of additional cash crops or to ensure smooth expansion of existing cropping systems, have not been taken into account to try and further limit the project areas.

## The targeting system set up for the China 2001-2005 CP raises a series of issues:

- VAM screening criteria have sidelined other criteria such as total available food aid for the selected area, environmental-geographical criteria and the existence or not of certain opportunities to substantially improve rural income (agricultural production or income generation through migration to other areas); and

- Overall targeting has overwhelmingly influenced the design and implementation of the programme, as too many townships and communities have been selected in view of the limited food available and counterpart funding (with dispersion of activities so that each poor household gets an 'asset'.

### Participatory Process

## The utilisation of a participatory process in project preparation, planning and implementation is unanimously acclaimed by beneficiaries and PMOs at different levels. The process adopted through creation of Village Implementation Groups and elaboration of Village Development Plans (VDP) by the village communities is recognised to empower the village population and design project activities which better match the actual needs of the villagers.

## VDP processes gave priority to the poorest households. Self-assessment of wealth by the villagers through a transparent method, which involves the common agreement of the population, has proven to be an efficient approach (e.g. in Gansu Province) to targeting the poorest. All beneficiary households visited by the evaluation mission are poor with annual income per capita before the project between 200 and 500 CNY with some extremely poor who are generally disabled or single-person families.

## The recommended division of households in 3 categories of wealth (poorest, average and less poor), in order to target the poorest-of-the-poor, has been differently approached in different projects. Generally, self-estimation by the village communities (as implemented in Gansu) revealed to be less time-consuming, simpler and more efficient than systematic interviews of each household made by PMO staff (method adopted in Guangxi). In this latter case, the heavy workload and expenditure borne by the PMO have been perceived as a real burden, while the farmers’ commitment was not encouraged. Self-assessment by the villagers themselves proved to be an efficient approach to targeting the poorest. Moreover, this method is transparent and requires the village population to reach a common agreement.

Examples of Village Implementation Maps and Plans- South Gansu Integrated Rural Development Intervention

### Integration of Activities

## Activities design at village level were made to fit the amount allocated. Through the participation process, farmers allocated activities according to their knowledge of the actual individual households situation, needs and capacities. The existence of the VDP and its good implementation under the guidance of the VIG has certainly partially compensated the lack of definition of links between different components in the design and the scarcity of resources allocated per village and per household.

## Provincial PMO played an important role as well in coordinating the intervention of different technical bureaus and organisations (agriculture, animal husbandry, water conservancy, health, education, and women federation), so that the overall programme benefit from the necessary technical advises. The administrative structure and organisation in China seldom permits synergy between different technical units. The organisation of the WFP/IFAD-assisted projects under the CP is recognised to have created the conditions for an effective coordination of technical assistance, in which the PMO plays and active coordinating role.

## C.	Implementation of Basic Activities

### C.1	Investment in Human Capacity

## According to the CP, 24 percent of the total resources were to be dedicated to investment in human capacity. This percentage was maintained despite the low level of contributions. 72 percent of the planned resources for this activity were available to WFP for distribution The objectives were to: (i) increase literacy, especially for women; (ii) improve technical and management skills to raise awareness of basic health and nutrition, especially for women; and (iii) improve the implementation capacity of the Government.

Table 5 - Total IRD Component (WFP Assistance) 2001-2005 per Activity as of May 2005

| Activities | Beneficiaries | Tonnages |
| --- | --- | --- |
|  | Plan | Actual | % | Planning | Act | % |
| Investment in Human Capacity | 4,724,400 | 4,133,488 | 87% | 84,196 | 60,718 | 72% |
| Land development and irrigation | 2,480,000 | 1,072,906 | 43% | 144,565 | 99,644 | 69% |
| Social infrastructure | 1,267,600 | 574,600 | 45% | 64,727 | 31,794 | 49% |
| Water & Soil conservation | 976,800 | 587,799 | 60% | 53,024 | 38,037 | 72% |
| Total CP | 4,724,400 | 4,133,488 | 87% | 346,512 | 230,193 | 66% |

##### Design

## The strategic objective of the Investment in Human Capacity activity component of the CP is to “enable poor households to invest in human capital through education and training”. All beneficiaries’ households were foreseen to participate in this component.

## The component proposes training programmes, targeted primarily to women, and executed at three clearly formulated levels. The first level covers basic functional literacy course over a 60-days training period followed by a refresher course. A second level addresses the technical and managerial skills of candidates for IFAD-supported loans for income-generating activities through a 10-days training course, which should start only once IFAD loan disbursement mechanisms are in place. The third level consists of basic health and nutrition courses that address micro-nutrient disorders, reproductive tract infection among women and improve women’s knowledge of balance dietary practices for themselves and their children. Complementary activities are supported by government counterpart, including training for trainers, schoolteachers, village doctors and midwives.

##### Achievement of Objectives

## Training is definitely welcome by farmers who usually hardly have the opportunity to attend any type of training. Literacy training is particularly appreciated by women whose literacy rate before the project reached up to 70/80 percent. With basic literacy background, they can start looking for off-farm sources of income and employment. With technical training, they can better diversify their sources of income, including through the development of agricultural activities. The proportion of men to women attending training stands between 1.6/1 and 2/1, which remains satisfactory according to planned targets (80 percent).

## Food aid for training is especially adapted to encourage women in attending trainings. Without food support, women would likely not attend training which are time-consuming and divert them from their daily necessary activities in agricultural production, child and house care. Trainings are held in the villages which is another pre-requisite for women to participate.

## The main weakness of all types of trainings delivered through the project assistance is certainly the lack of development of specific teaching material adapted to local conditions and continuously up-dated. In order to achieve better efficiency, a variety of training material could have been developed including posters, pictorial supports, and tapes for technical training. To this respect, training of trainers could have played a fundamental role especially regarding communication skills, training methods and tool development, participatory training and adaptation of the training content and method to the needs of each group.

## Literacy training has been constrained by the availability of WFP resources in 2003 and 2004 resulting in a further reduction of beneficiaries. In Litai village (Gansu Province), where illiteracy rates amounted for 50 percent for men and 70 percent for women in 2002, only 25 adults among 555 could attend the literacy course. For technical skills training, the actual 4 to 5 days delivered (versus 10 days planned) is not sufficient for farmers to gain solid and sustainable knowledge.

##### Summary of Main Findings and Observations from Field Visits

(a)	Functional Literacy

Design

- Targeted to illiterate population, especially women;

- Functional literacy training combines literacy and basic knowledge on health, nutrition, credit, and also covers various practical skills for agriculture and animal husbandry, income generating activities, and administrative and legal empowerment;

- Training textbook developed by the Women Federation is recommended; and

- The course comprises a first training followed by a refresher training one year later for about half of the graduates of the first part.

Findings

- Literacy training is highly appreciated by villagers, and especially women;

- In both projects visited, WFP support has been reduced compared to what foreseen in IFAD technical documents (50 training days for the basic course plus 30 for the refresher course in Guangxi, and 30 training days in total in Gansu), which was already limited compared to what foreseen in the CP (60 days of basic training plus a refresher course);

- In Guangxi, functional literacy training was finally compensated with 40 family rations for 120 training sessions (IFAD technical document);

- Support for development of training material has apparently not been considered, neither methodological support for development of the training curriculum development or teaching methods; and

- One person per village was trained as trainer in Gansu, which could largely assist the community in the future.

- Technical and Managerial Skills Training

Design

- Addresses women (and men to a lesser degree) who have already general basic education but want to refresh their skills to acquire technical and managerial skills;

- Aims to enhance their capability for agricultural production and to participate in project supported credit schemes for income generation; and

- The training will sharpen simultaneously literacy and numeracy skills with the specific technical content.

Findings

- Duration and food compensation for the training was expected to vary according to content, with an average of 15 days for the complete course. Both durations and rations were reduced in Guangxi (2 to 7 days per training session, 1 family ration for 2 working days).

(c) 	Basic Health and Nutrition

Design

- The IFAD technical documents state clearly the objectives of the training, its content, who should participate, and what should be the methodology adopted during the training;

- It covers a variety of topics, including nutrition particularly at different critical stages of life, reproductive health care, individual hygiene and infectious diseases prevention, importance of drinking water, and human and animal waste disposal;

- It is meant to tackle specific health problems in each county; a health advocacy group should be set up in each new township clinic built for following-up health and sanitation status in the project area and recommend topics for village training;

- Targeted beneficiaries are women of reproductive age, which should participate 3 times into a training during the project lifespan period, women will receive a half day; and

- Simple handouts with practical health knowledge that use a simple language and that are illustrated.

Findings

- Health and sanitation training for women could most of the time not be differentiated from other types of training by the beneficiaries. Literacy training did actually combined basic notions about health, childcare and sanitation.

(d)	Overall Observations

- Importance of the duration of the training which should be sufficient for trainees to understand and absorb the content;

- Importance to develop specific teaching material adapted to local conditions and continuously up-dated;

- Training of trainers plays a fundamental role;

- Training largely involved the intervention of different administrations, which bear the trainers’ fees, transportation, and accommodation. It is essential to define clearly who will support these costs; and

- The content of three types of trainings did sometime overlap, a certain flexibility in combining different types of training could be recommended.

## By the end of 2004, at least 70 percent of the foreseen beneficiaries had been trained, all categories of training included except literacy training in West Guangxi, where the choice was made to finance first infrastructure construction when running out of food aid in 2004. Priority was obviously given to technical training, which number of beneficiaries reached more than 80 percent of the target.

## The duration of the courses has been often considerably shortened as compared with what had been foreseen in the original CP design. A first reduction occurred during project preparation (see “WFP agreement” which refers to the document prepared by IFAD), followed by a second reduction during implementation, likely as a consequence of limited availability of funds. To this respect, high quantitative achievements compared to target in the South Gansu project, after a two-years running period, should not be misleading. Preference was given to the number of beneficiaries versus the duration and quality of the training provided.

## C.2 	Land, Water and Natural Resources Components

## Agricultural development and natural resources management have been addressed in the CP through the implementation of two components: (i) Land Development and Irrigation; and (ii) Land and Water Conservation which are however closely linked and have thus been considered jointly in the evaluation. According to the CP, 57 percent of WFPs food aid were to be dedicated to these two activities. This was maintained in spite of the low levels of funding. 71 percent of the planned resources for these activities were available to WFP for distribution.

Table 6 - Outputs from Standardised Project Reporting

| Land Development and Irrigation | Unit | Planned | Actual | Total % |
| --- | --- | --- | --- | --- |
| New irrigated farmland | ha | 17 173 | 12 296 | 71.6 |
| Irrigated farmland rehabilitated | ha | 9 912 | 10 806 | 109 |
| Irrigation systems established | nber | 12 775 | 5 510 | 43.1 |
| Irrigation systems rehabilitated | nber | 48 | 38 | 79.2 |
| Canals rehabilitated | km | 1 422 | 1 012 | 71.2 |
| Dams-ponds constructed | nber | 19 196 | 20 725 | 108 |
| Dams-ponds rehabilitated | nber | 11 | 10 | 90.9 |
| Terraces constructed | ha | 12 051 | 8 151 | 67.6 |
| Terraces rehabilitated | ha | 1 247 | 1 129 | 90.5 |
| Land improved | ha | 19 342 | 17 08 | 88.5 |
| Demonstration compensation | ha | 600 | 267 | 44.5 |
| Check dam | nber | 2 626 | 1 220 | 46.5 |
| Water and Soil Conservation | Unit | Planned | Actual | Total % |
| Trees planted for forestation/reforestation | nber | 4 156 112 | 3 924 371 | 94.4 |
| Trees planted for forestation/reforestation | ha | 6 369 | 6 152 | 96.6 |
| Land with soil conservation | ha | 43 846 | 32 160 | 73.3 |
| Grassland | ha | 1 333 | 570 | 42.8 |
| Chinese herbal medicine | ha | 1 018 | 552 | 54.2 |
| Biogas units | nber | 25 024 | 26 961 | 107.7 |

## Both CP Components 2 (Land development and irrigation) and 4 (Land and water conservation) are closely linked and need to be implemented together both in time and in space. They also address the same beneficiaries. These two components have been dissociated when presenting the CP in order to highlight that part of the programme was addressing asset creation in the lower lying areas and natural resources conservation on the steeper slopes, but in the same water shed or natural resource base. This distinction was intended to show that these two groups of interventions were addressing different EDP focus areas. However, these two components are closely linked and considered jointly in this evaluation.

##### Design Issues and Relevance

## A wide range of activities has been implemented and results are impressive. For the Land Development and Irrigation Component, the activities were: upgrading of irrigation systems, construction of crop water cisterns, small river weirs, hill-side tanks, drainage ditches, terraces, land levelling and deepening of soils. For Land and Water Conservation Component the activities were: protection of key irrigation systems, road infrastructure and riverbanks through planting of environmental-economic trees, planting of nurseries and firewood lots, closing natural forestry areas, development of upland pastures, introduction of medicinal plants and construction of small biogas units.

## Technicalities were to be simple and easily managed by the beneficiaries with provision of basic technical training. Activities were to be harmonized through a VDP. However, more often than not the design of activities has been geared more at meeting individual short-term household basic needs than investing in much large community based assets. The main project partner has been the administrative village, but because of the remote and mountainous location of many activities, a focus on the hamlets within one micro-shed may have achieved a more integrated approach. While overall achievements are remarkable, impact on the overall natural resource base has been somewhat diluted by an attempt to encompass as many beneficiaries as possible with limited resources.

## Detailed planning and design has been carried out at village level and not at micro-shed level. The major project partner has been the village, i.e. the administrative village. In remote and mountainous areas, planning of activities should have been more focused on smaller village groups, such as communities or hamlets, which often depend on one micro-shed for livelihoods. At this level, it can be possible to complement the work carried out at administrative village level, which is to select areas within the village that are the most dependant on fragile and vulnerable environments and where production is easily jeopardized when climatic or natural conditions are unfavourable or where a higher number vulnerable of households dwell. Once these areas have been identified and agreed on by the village implementation group and administration, further participatory planning has to be carried out with the communities that live in these smaller areas. From the field visits it appears that too little attention was paid to developing activities in an environmentally integrated and development sustainable way. VDPs seem to remain more like one-shot operations with little updating or expansion during project intervention.

##### Summary of Main Findings and Observations from Field Visits

## Five major groups of activities were foreseen in the Provinces visited by the mission. As the mission could not access the technical annexes of the contractual documents between WFP and the Government, these groups of activities have been reviewed mainly from the following documents: (a) the WFP activity profile 9997.00 for the West-Guangxi project; and (b) the formulation report prepared in December 2002 for WFP. These two documents only relate to the WFP related issues in these two in principle WFP-IFAD joint projects. Furthermore they are too succinct regarding the technical descriptions of the various activities. So for the assessment of these various activities and the appreciation of their overall relevance, the IFAD working papers relating to crop and livestock production, land improvement activities and forestry have been used extensively. The overall findings and observations are as follows:

(a)	Food and Cash Crops

Findings

- no definition of the type of demonstrations to be implemented by the project; i.e. traditional farming cropping package promotion demonstrations or support to specific farming practices linked to other project activities;

- lack of details on demonstration programme (calendar and locations) and technical training curricula, contents, timing and methodology;

- lack of integration of activities in a comprehensive support to improving extension services;

- technical training designed in a top down manner and no linkages to farmer groups or organizations;

- activities implemented as stand alone activities by WFP and no or minimum integration with other activities; and

- work norms have not been substantiated through a precise technical terms of reference of what they should be done.

Observations

- importance of a successful integration and operational partnership with another donor or institution to ensure a comprehensive extension package;

- importance of integrating technical trainings and demonstration with other project activities; and

- design needs to go in hand with the emergence of farmer groups and involve farmers more in the extension itself.

(b)	Land Improvement (Irrigation)

Findings

- most of the activities under this component are the construction of small individual household water tanks or cisterns or stand alone works;

- water tanks are too small in capacity or in number to effectively provide farmers with a sustainable productive asset which is in fact either an area of staple crop or of income generating vegetable or fruit production;

- lack of additional water conservation farming techniques to save and manage water at field level and lack of additional works on improving water interception to the tanks or cisterns;

- lack of perception that intakes, pump stations and canal lining are elements of wider small- or medium-scale irrigation systems, where distribution of water is the final purpose and which should be managed and operated by water users or farmers groups. This element of future ownership of the systems has not been promoted and supported by the project;

- work norms are not clear regarding the way households are compensated for the skilled labour tasks that need to be carried out, idem regarding co-funding of non-food items; and

- work norms have been averaged for planning and design reasons, but these work norms have become the standard and reporting has not been designed in such a way as to check conformity with prevailing site specificities.

Observations

- importance of designing small scale systems with the farmers that will operate them and integrating all works in order to develop a sustainable and productive irrigated agricultural production in this area;

- importance of providing households with a sufficient number of cisterns in areas where small irrigation schemes are not feasible;

- importance of integrating additional extension activities relating to water conservative farming techniques at field level; and

- design needs to go in hand with the emergence of farmer groups that will co-fund and operate the small irrigation systems.

(c)	Land Improvement (Dry Land Development)

Findings

- foreseen activities are very relevant and would be even more effective if they were planned and implemented within a participatory micro-watershed plan;

- village plans have stopped short of the step of taking the design down to field level with those communities living in fragile micro-watershed;

- additional biological stabilization and protection measures were foreseen in the IFAD working document but dropped by WFP;

- there is little evidence that these land improvement works have been complemented by the promotion and extension of appropriate conservative farming systems and techniques;

- activities implemented as stand alone activities by WFP and little integration with other activities;

- work norms are excessive in Guangxi if compared to other WFP bench marks in similar areas;

- compensation for the skilled labour tasks that need to be carried out, has not been foreseen; and

- work norms have been averaged and have not been adapted during implementation to local conditions on a watershed basis.

Observation

- importance of designing and working on an integrated way within micro-watersheds, in close linkage with local farmers groups and the participatory village level planning exercise;

- importance of providing households with a compensation package to be able to mobilize enough labour (household plus kin or neighbours) to participate in these more community-based works;

- importance of integrating additional extension activities relating to water conservative farming techniques at field level;

- importance of linking land improvement with the national policy of returning marginal productive slope to forestry and/or pastureland; and

- importance of also including ridge stabilization techniques and works.

(d)	Livestock Development

Findings

- is farmyard livestock intensification through a cut and curry system with Luzerne based fodder production sustainable in a mountainous loess environment?

- lack of integration of two WFP-supported activities with a wider and comprehensive support to improving animal husbandry and veterinary services;

- lack of a detailed description of what is to be done under the WFP-supported activities, i.e. technical indications and designs and importance and destination of additional funding of non-food items; and

- activities implemented as stand alone activities by WFP and no or minimum integration with other activities.

Observations

- importance of the preliminary analysis of constraints and selection of activities in fragile environments;

- importance of a successful integration and operational partnership with another donor or institution to ensure a comprehensive package; and

- need for good assessment of activities to be supported.

(e)	Tree-Based Ecological Development

Findings

- little integration of forestry activities with overall community based micro-watershed planning and lack of community based natural forestry management plans and agreements;

- WFP's support has been more limited than what was planted for in the IFAD technical documents, focusing on conservation, fuel woodlots and individual tree plantations;

- support to village forest guards through a combined cash and food taken is questionable;

- work norms do not provide for compensation of tree watering during the first years (essential in Gansu dry loess area);

- fruit tree planting is included in forestry and should be under agricultural cash crop production; and

- no work has been foreseen to plug ravines and gullies within the areas where the project is operating.

Observations

- importance of a designing and working on an integrated way within micro-watersheds, in close linkage with local farmers groups and the participatory village level planning exercise;

- importance of linking land improvement with the national policy of returning marginal productive slope to forestry and/or pastureland; and

- importance of setting up sustainable working systems between bureaus and farmers groups that can handle cross cutting problems such as gully plugging and fruit tree developments.

##### Achievements in Guangxi and Gansu Provinces

Achievements as Reported

## Implementation of these various activities is reported to be carried out as originally planned. Implementation was however delayed by late arrival of food and reduced deliveries during 2003-2004, with no automatic stepping in by GOC as used to be done previously. Furthermore, IFAD delayed its intervention in Gansu, where the overlap between the two partners is reduced to 4 counties only.

## Figures provided show that in Guangxi activities under the two components reviewed are close to completion, percentages of completion varying from ± 80 percent to over 100 percent, with the exception of 4 activities which are around 70 percent completed. One activity, related to the construction of small traditional river diversion weirs, has not been implemented. Guangxi project does not seem to have suffered too much of the delayed provision of WF food.

## In Gansu province, with only one more year to go, progress is low, as percentages are all below 40 percent (varying between 10 and 40 percent). In view of these figures, of the delayed start-up of the project, in a year where WFP's food aid provision to China was low, and of the delayed start up of the IFAD partnership, it seems unlikely that this project will be able to achieve its targeted outputs if WFP's food is terminated as foreseen in December 2005. The project will not have had the time (less than three years of effective implementation) to ensure that the related software aspects have been completed. People and communities also need to benefit from other non food related supports, which IFAD and/or the Government needed to implement.

## The M&E reporting does not provide any geographical information, which could easily have been done on the basis of the GIS work already produced by the WFP-IFAD VAM unit. The implementation of both the programmes is based on VDPs, but reporting does not provide any indication on how these plans are progressing and which areas are concerned.

Mission Findings

## Activities seem to be stand alone activities. There is little evidence that these assets have been provided in an integrated manner. For example, water cisterns are one step towards water conservation at field level, they by do not mean that the farmer has access to irrigated agricultural production. In several places farmers insisted that one tank provided a means to store water over winter to carry the crop through the first spring months but that this was insufficient for an all year round irrigation. Water tanks without participatory extension of water conservation planting and cropping systems is just a step with a limited impact on crop production. The same can be said regarding terracing and land levelling or soil deepening activities, where the most important is what and how crops will be planted on the improved land. Conservation plantation without addressing the gully formation, as was witnessed during field visits in Lixian, similarly indicates that stand alone assets are not sustainable and are often just a very first step to mobilize communities.

## Dry land improvement requires a continuous support of extension staff. From farmers’ interview it seems that this has not always been the case, except for the initial “technical instructions” type of training provided by the township and/or county extension stations. This reverts to a wider lack of clear national agricultural extension policy and strategy framework. Little participatory extension and farmers oriented research is being implemented. WFP-supported projects however require such an approach putting a strain on the various township extension stations involved.

## Assets are too focused on individual households; there are no wider community based activities to be supported through community food-for-work. During field visits, there was some concern that more important and community based works such as access tracks or paths, small access roads, sanitation works at village level, more comprehensive soil conservation works (such as gully plugging) do not seem to have been included in the various VDP work plans.

## Combining local labour intensive community works and developing household level assets would have allowed to provide the various households in these communities with a sufficient amount of labour opportunities to effectively cover most of the food gap and to create a sufficiently attractive amount of local off-farm income to attract some of the local migrant farmers to stay temporarily and to participate in these works. An illustration of this combining individual asset and other community based assets is presented in the slide on the following page.

## VDPs are a good innovation, but this important break-through in the design and planning of WFP-supported activities would have needed substantial TA support to assist PMOs in getting the VDP well on track and away from a simple transcription at village level of quantities of assets that the township has planned for each village in line with what is available for the county on a whole. VDP are made at administrative village level. Both in Guangxi and Gansu, administrative villages are composed of a number of hamlets or village communities that do not live in the same watershed or landscape environment. The VDP concepts still needed to be extended to those hamlets and communities identified through the VDP as being the poorest or the target communities to be supported.

## Designing a more comprehensive micro-shed participatory plan with the communities living in small hamlets, would address a series of wider community works that benefit all inhabitants of the hamlet or micro-shed. This would in turn provide a longer term framework over two to three years during which individual poor households could receive additional support to the spot activities designed so far (see slide on following page, where the suggested interventions can only be achieved if interventions continue over a certain period of time).

##### Work Norms

## Work norms have been reviewed by the evaluation mission in the two Provinces visited and are presented in the following table.

## It appears that global work norms have been estimated for activities and that these have become embedded as such, as no detailed design of activities per site is reported. They seem also to be the basis of the reporting back to WFP. The only exception that can be reported concerns the Gansu project where three activities seem to have used far more workdays than planned: (a) compensation for demonstration fields (1,124 work days instead of 300 planned); (b) establishment of grassland (1,359 work days instead of 450 planned); and (c) establishment of medicinal herbs (1,719 instead of 750 planned). The yearly M&E form does not provide explanation for these three discrepancies.

## Various inconsistencies in these average work norms have been found, which are the result of a lack of detailed technical descriptions for some project activities and a lack of technical appraisal. Some discrepancies in work norms have been found when bench marking work norms relating to dry land improvement with norms used in previous WFP projects in similar environmental conditions. Average work norm ranges should be available and, if the increase is justified, the technical appraisal should have substantiated it.

## For budgeting purposes average work norms, based on a series of typical designs, can be used for simple activities. Some standard activities such as water tanks and water cisterns also depend on the natural of the materials used, the nature of the soils to be excavated and the available land on which to build the tank or cistern. For more complex activities such as lining of major canals, rural feeder roads, terracing, where site sitting is essential to estimate the work load, it is essential to agree on a set of basic elemental work norm for individual tasks needed to complete the overall work. During implementation these activities need to be constructed after designs have been tailored to local conditions and bills of quantities adapted.

## Reporting has been drastically simplified and this has consequently concurred to embedding the average work norms as standard “multi-purpose” norm for a specific kind of activity. In the Gansu project for example, the working papers had foreseen four different sizes of irrigation water cisterns, three different forestry activities and four different sizes of drinking water cisterns. SPR and M&E form have simplified the reporting to one single irrigation water cistern model, one forestry activity and one single drinking water cistern model. Reporting does thus not provide any detailed information on which size is the most appropriate or which forestry activity has been the most implemented.

### C.3 	Social Infrastructure

## According to the CP, 19 percent of WFPs food aid were to be dedicated to investment in social infrastructure, which was almost maintained (actual distribution amounted to 15 percent of total distribution of the CP). 49 percent of the planned resources for this activity were available to WFP for distribution. The main objective of this activity component was to reduce the physical and economic isolation of poor families by improving access to markets, health facilities and safe drinking water, and to reduce the workload for women. More specifically, the construction or rehabilitation of the following infrastructure and assets has been supported by WFP: village roads, village wells, retention ponds, household piped water systems, fuel-saving stoves, latrines and village dispensary for primary health care. Physical progress in social infrastructure construction is, in general, satisfactory.

Table 7 - Outputs from Standardised Project Report (2001-2004)

| Social Infrastructure | Unit | Planned | Actual | Total % |
| --- | --- | --- | --- | --- |
| Road construction | km | 416 | 381 | 91.6 |
| Water cisterns – hand pumps installed | nber | 21,728 | 13,933 | 64.1 |
| School buildings rehabilitated | nber | 2,487 | 1,271 | 51.1 |
| Health posts rehabilitated | nber | 2,048 | 218 | 10.6 |
| Vegetable gardens improved | nber | 400 | 80 | 20.0 |
| Drinking water systems | nber | 46,809 | 35,728 | 76.3 |
| Toilet improvement | nber | 22,390 | 17,091 | 76.3 |

## Construction of domestic water supply systems has an immediate impact on rural livelihood, providing clean water where villagers previously used polluted water from rivers, or had to rely on water sources located 2 to 3 hours walk from the settlement. Road construction improves accessibility to the villages; however the impact will become obvious only when farmers will have access to vehicles. Biogas digesters associated with construction of latrines work well in Southern China, but necessitate the ownership of livestock and therefore cannot be accessed by poor households who generally cannot afford raising livestock.

## Resources allocated to social infrastructure activity were neither sufficient to cover the needs of all households in one village, nor the needs of a village comprehensive sanitary development plan. Evidence was found in the two projects visited that water collection and storage infrastructure built by the project did not meet the current consumption needs, whether the number of domestic water cisterns was insufficient (e.g. 21 cisterns for 205 households in Litai village in Gansu) or their storage capacity could not meet the households needs (Guangxi). Social infrastructure activities seem to have been implemented as stand-alone activities, with no attempt to link with other projects activities.

## Within the project design, there is little possibility to support local community initiatives outside of the strict project framework. Rural roads construction shows a clear example where rural feeder roads have been constructed through County level planning with the assistance of the project, while beneficiary villages needed to improve paths and tracks (not included in the project) before having themselves access to the new constructed feeder roads.

## There is no evidence that the workload of women has decreased through social infrastructure building. On the contrary, during the duration of the project, the workload of women increased due to the fact that they bear an important part of the labour necessary for construction since men are away part of the year, employed seasonally out of the farm

##### Summary of Main Findings and Observations from Field Visits

(a)	Drinking Water Facilities

Findings

- Activities are relevant at household level but could be improved by adding simple individual sand filters, by working on the catchment area (surfacing or improving interceptor drains and springs) and ensuring pumps are effectively provided;

- small water supply systems need to be designed and implemented through water users groups as they will need to be maintained and operated by the communities once the works are completed;

- both projects do not foresee any work on sanitation either at household level or at community level. Most remote communities are not drained at all when major rain events strike and are not provided with proper minimum sanitation works;

- work norms for the tanks and cisterns need to be coherent within a same project area, between drinking water tanks and irrigation tanks; and

- work norms for water supply systems are fixed on an averaged basis and do not seem to be updated during implementation.

Observations

- Importance of providing a wider asset than just a cistern or tank;

- importance of combining water and sanitation activities with community based health education and other primary health care activities;

- water and sanitation need to be assessed and addressed at community level and community based activities undertaken in order to improve the overall community, hamlet or village conditions; and

- work norms need to be coherent within each project area and those for community based works need to be updated during implementation on a case by case basis.

(b)	Rural Feeder Roads

Findings

- One province had planned rural roads which have not been supported by WFP but directly through IFAD funding;

- the other province has included roads without any preliminary design and planning;

- priority has been set in the two project provinces at establishing sections of rural feeder roads through county level planning;

- no activity has been included to support local community initiatives to improve access paths and tracks, stairs and steps in and around villages and communities;

- activities implemented as stand alone activities and there is little evidence of how the intended sections link up with other project activities; and

- work norms have been estimated on an average Km design basis in 9 counties in West Guangxi and need to be constantly checked and updated during work implementation. In South Gansu an average work norm which is half that of West Guangxi has been used but not substantiated.

Observations

- Importance of integrating access roads and the outcome of the various VDP or VIP;

- there is scope to plan specific and smaller interventions at community level to improve intra-village mobility through better watershed and mobility planning; and

- food support to road works cannot be implemented on an average per km base. The work norms used for design and budget framing needs to be constantly monitored and based on actual bills of quantities and work progress. The M&E tables used by WFP are irrelevant in that respect.

(c)	Rural Clinics

Findings

- The existence of rural clinics in West Guangxi facilitates the organisation of vaccination campaigns for children and health checks and awareness for pregnant women; and

- this component was not implemented in South Gansu.

(d)	Schools

Findings

- Grade 1-3 schools built within the project welcome already a high number of children and operate in full-capacity; and

- this component was not implemented in South Gansu since it is not in line with the recent government policy to reduce the number of villages’ schools with grades 1-3 to the benefit of comprehensive boarding schools.

## By the end of 2004, more than 90 percent of the target beneficiaries had taken part in social infrastructure construction in West Guangxi, except for school buildings, which involved only 75 percent of the planned beneficiaries. In the South Gansu project, progresses are much more limited, and 32 to 45 percent of the planned beneficiaries have been involved in social infrastructure construction. This is partly due to the shorter implementation period of the project, and to the limited availability of funds, which resulted in prioritisation of activities.

## Actual work norms used for the construction of social infrastructure do not differ from the norms foreseen in the preparation documents elaborated by IFAD appraisal missions, except for water supply systems (57 percent of the original work-norm) and the community water tanks (77 percent of the original work-norm) in West Guangxi. In general, work-norms are standardised, do not take into account local differences, lack of coherence within the same area, and do not seem to have been up-dated during project implementation.

D. 	Socio-economic Impact and Beneficiary Participation

### Beneficiaries

## Beneficiary participation in the implementation of the CP’s basic activities is massive and active. Examples from the provinces visited by the evaluation mission can illustrate this involvement: the total number of persons who benefited from project activities until end 2004 in Guangxi Province is 682,701 (92 percent of the target and 55 percent of the total population of the project counties, of which 60 percent are women) and 936,177 rural inhabitants in Gansu Province (82 percent of the target, of which 50 percent are women).

## The results for the overall CP show that the annual number of beneficiaries decreased over years from 2002 and 2004, due to food-shortfalls. Nevertheless, as of May 2005, the programme has reached 87 percent of the planned number of beneficiaries.

### Household Food Security and Self-reliance

## All villages targeted by the CP face food gaps resulting from a combination of scarcity of cultivated land and poor natural and economic conditions regarding agricultural production. The annual food gap duration ranges from 4 to 6 months.

## According to interviews held with groups of households and to the food ration leaflets received from the project by the beneficiaries; the actual WFP food aid received per household for both FFW and FFT could, on average, cover 8 to 21 percent of the annual food gap.

## The annual food gap has been reduced from 4 months to 1.5 month. In the short-term, the quantity of grain received from WFP covered a small part of the annual food shortage. Each household received between from 130 kg to 300 kg spread over three years, which would cover one to two months’ food shortage per year for a five person household. Land development and infrastructure construction had a major impact on household long-term food security through increased grain yields, estimated at least at 30 percent by the farmers.

Table 8 - Examples of Average Food Rations Supported by WFP in Visited Villages

| West Guangxi Poverty Reduction Project | Fengshan County | Tian’er County |
| --- | --- | --- |
| Annual food gap duration | 4 to 5 months | 4 months |
| Estimated food gap/4 persons’ household | 320 to 400 kg | 320 kg |
| Average actual WFP support/household over 4 years | 104 kg | 272 kg |
| Average actual WFP support/household/year | 26 kg | 68 kg |
| Percentage WFP support vs actual food gap | 8 | 21 |
| Corresponding family rations | 37.4 | 83.8 |
| Among which FFA | 35 (93%) | 75.5 (90%) |
| Source: Households groups’ interviews, Evaluation mission, May 2005. |

## The impact of WFP food aid has been adversely affected by the food shortfall that occurred in 2004. Table below shows that during the first two years of the project, in 2002 and 2003, the food aid covered more than 40 percent of the food gap, whereas it could only supplement 7 percent of the annual food gap in 2004, and 12 percent in 2005.

Table 9 - Example of Food Support Received by Household Spread over Years

| Year | FFT | FFA | Total WD | Food Help (kg) | Food Gap (kg) | Percentage WFP Support Versus Food Gap |
| --- | --- | --- | --- | --- | --- | --- |
| 2002 | 2 | 39 | 41 | 133 | 320 | 42 |
| 2003 | 5 | 40 | 45 | 146 | 320 | 46 |
| 2004 | 7 |  | 7 | 23 | 320 | 7 |
| 2005 |  | 12 | 12 | 39 | 320 | 12 |
| Total | 14 | 91 | 105 | 341 | 1,280 | 27 |
| Source: Four persons-household food rations leaflet, West Guangxi, May 2005. |

## The major impact on household food security is achieved through land development and infrastructure activities, which result in increased and stabilised grain yields. In Guangxi, maize yields could increase from 150-200 kg to 250-350 kg per mu after terracing and irrigation schemes implementation. The increased production can be used to fill the food gap or to animal husbandry, which will bring the household a steady source of cash income. Improved paddy fields irrigation results in spectacular increased in yields (up to 75 percent). Through land improvement and irrigation, the annual food gap has been reduced from 4-5 to 1-1.5 months.

Table 10 - Increase in Yields through Land Improvement

|  | West Guangxi | Range of Increase in Yields (percentage) | Land Improvement Through |
| --- | --- | --- | --- |
|  | 2002 | 2004 |  |  |
| Paddy yield (kg/mu) | 150 | 200 | 250 | 350 | 67 | 75 | Irrigation |
| Improved arable dry | 0.5 | 2 |  |  |
| Maize yield (kg/mu) | 100 | 150 | 150 | 200 | 50 | 33 | Terracing |
| Source: Households interviews, Evaluation mission, May 2005. |

### Poverty Reduction

## A comparison between the situation before (2002) and after the project (2005) shows that the average annual income per capita increased from 200 to 500 CNY to 400 to 800 CNY. This impressive improvement is largely due to increases in yields, diversification of agricultural activities and of sources of income. Notably, the utilisation of fertilisers and improved seeds has contributed to a better crop productivity and the development of animal husbandry activities developed: increased potatoes and maize yields enable households to raise pigs and, in Northern area, grass growing combined with stable-fed goats has been supported by different programmes.

## In addition to the above-mentioned changes, a major transformation in the household’s budget lies in the diversification of sources of income. An increasing number of households have access to seasonal off-farm migration work, which income stands for at least 20 percent of their income. Whereas 3 to 4 years ago, farmers had rarely the possibility to look for off-farm employment opportunities, at present on average 1 or 2 persons per household is working outside temporarily, mostly in construction works and come back for the spring festival and during the agricultural labour peaks. Off-farm jobs are the only opportunity for farmers’ households to lift themselves up, though employment is hazardous and payment not guaranteed. Without off-farm sources of income, local resources are too scarce to sustain the expenditures of the family, particularly school fees, which represent the most important expenditure of the households.

Table 11 - Changes in Average Income per Capita (2002-2004)

Unit: Yuan/Capita

| Project | County | 2002 | 2004 | Increase |
| --- | --- | --- | --- | --- |
| West Guangxi | Fengshan | 200 | 800 | x 4 |
| West Guangxi | Tian’er | 400 | 650 | x 1.6 |
| South Gansu | Li | 200 | 400 | x 2 |
| Source: Households groups’ interviews, Evaluation mission, May 2005. |

### Livelihood Improvement

## Literacy programmes have undoubtedly a great impact on the villages’ population. This is particularly important for women who are not given the priority for schooling. Access to literacy, agriculture, health and sanitation training, even limited to the very basic knowledge, is an opportunity for empowerment through better information, and eventually better chances to access other sources of income.

## Improved literacy rates, increased awareness of women in basic health and nutrition, better domestic water supply, and improved agricultural production resulting from the project had a start-up effect in terms of livelihood improvement in the project villages. However, available resources have been widely spread among an important number of villages. Consequently, resources allocated to each single village were not sufficient to implement a sound, comprehensive and sustainable development plan. In that respect, provinces have adopted different solutions. In South Gansu, only part of the households (10 to 15 percent) could benefit from village sanitation measures (domestic water supply and latrines), while in West Guangxi, most of the villages’ households (60 to 75 percent) could get a water cistern, but the storage capacity was not sufficient to cover the needs of each household.

## There is evidence that land improvement and irrigation are major pre-requisites for creation of sustainable development. In villages visited where these activities were not implemented, the poor population is left without sustainable production assets and are likely to slip back into poverty when project ends.

Table 12 - Impact of Human Capacity and Social Infrastructure in Villages Visited

|  | South Gansu | West Guangxi |
| --- | --- | --- |
|  | 2002 | 2004 | 2002 | 2004 |
| Women illiteracy rate | 70% | 40% | 80% | all trained |
| Men illiteracy rate | 50% | 30% | 50% |  |
| Adult population who received technical training |  | 60-75% |  |  |
| HH with drinking water cisterns |  | 10-15% |  | 60-75% |
| Source: Households groups’ interviews, Evaluation mission, May 2005. |

### Impact of WFP CP in the Context of China’s Economic Growth

## WFP outcome help cannot be separated from the other investments made by the government, IFAD, and the farmers themselves. Results could be achieved only through synergy. Moreover, the dramatic changes in the income and living conditions of the beneficiary households can be largely attributed to the effect of agricultural reforms and overall sustained national economic growth as it is the case since WFP support started in China. However, the CP began after 2000, and focused on poor farmers living in remote areas, in villages which remained without electricity supply and who were still too isolated to benefit from off-farm jobs offered by the growing industrial and construction sectors. In that respect, WFP support through the CP is outstanding. Internationally-funded investment programmes and poverty alleviation programmes lead by the Chinese government usually do not reach the poorest of the poor. The only support received by this poorest villages had been relief food from the government and monetary or grain compensation for the conversion of cultivated land in prone to erosion areas into forest or grassland by the recently implemented national Land Conversion Programme.

E.	Gender Aspects

## Mission findings are based on a desk review carried out in the Country Office in Beijing and field visits Guangxi and Gansu provinces. To appreciate project impact on gender-related aspects, mini-PRA exercises were undertaken in some villages in two provinces visited by the mission. WFP gender policies and its development in China were thoroughly reviewed and findings from the case studies of “Good Practice and Insights/Lessons from the Operationalization of WFP’s Commitments to Women were taken into account during the evaluation.

## Women in WFP projects in the early nineties in China were not yet explicitly a specific target group at the time of preparation, planning, appraisal or implementation and the beneficiary data were therefore not disaggregated by gender. This makes it difficult to appreciate project benefits for women in this period. However, women were recognized as equal partners and actively participated in the project activities, although mostly in labour-intensive food-for-work activities. The case studies show that approximately 42 percent of the participants were women. The number of women taking part in training programme remained low compared to the important role they played in poverty alleviation and food security. Technical training was also organized with the feature of men-domination due to high illiteracy rate among women. Women’s health and nutrient needs were not recognized at all.

## In September 1995 when the Chinese Government hosted the Forth World Women’s Conference in Beijing, both WFP and the Chinese Government made strong commitments to strengthen women’s position in development. Gender became a well-known “concept” and gender development has been given nationwide attention. A number of initiatives have been launched by the Government to strengthen women’s institution like All China Women’s Federation.

## A typical Women-in-Development (WID) sub-project was introduced to existing WFP Integrated Agricultural Development (IAD) projects and three IAD projects were expanded to insert Women’s Health and Micronutrient Facility component in 1994 in order to make additional efforts to better address women’s particular vulnerabilities related to health, access to credit and income. A WID workshop was conducted by the WFP CO in 1995 and a Gender-and-Development (GAD) workshop followed in 1996 to establish a gender sensitive mechanism by having a Gender Focal Point at all management levels. A Gender-and-Development approach was then put into practice instead of the WID approach, and a comprehensive gender policy; Commitments to Women 1996-2001 was launched.

## Based on the lessons learnt and experiences of partner agencies from the implementation of Commitments to Women, the Enhanced Commitments to Women (2003-2007) was developed, focusing on gender equality, empowerment of women and gender mainstreaming in the project cycle. The Gender perspectives in the CP were well aligned with the new WFP gender policy.

## The CP foresees that about 80 percent of FFT participants and 50 percent of Food-for-Assets (FFA) participants will be women. The implementation structure requires that women participate in project management groups such as Village Implementing Groups and Project Management Offices (PMOs). Related activities include management and leadership training for women in project management structure. Collaboration with ACWF in various training activities was foreseen. Reports and surveys for planning and evaluation collected gender-disaggregated data.

## WFP’s traditional food-for-work activities were reorganized along the Enabling Development principles and women become the biggest group benefiting from the CP interventions. In Guangxi and Gansu Provinces women’s participation in FFW was respectively 57 percent and 51 percent of the actual beneficiaries and for FFT it was 64 percent and 61 percent. Through the use of PRA tool the mission found that it was difficult to assess women’s access to and control over the assets created since households simply could not differentiate the ownership within the same household. Through PRA exercises, the mission found that the assets created are in line with the beneficiaries’ priorities, especially women. However, lack of information of outcome and impact level indicators in the monitoring and evaluation system limits the result interpretation.

## A prioritization exercise with the beneficiaries showed that women benefited most from the investment in human capacity compared to other activities, and therefore highly appreciated by women. However, the mission found that due to the limited resources and shortfall of WFP food faced during the year 2003-2004, training may not have been adequate since in some villages only women below age 40 were eligible for the participation to the functional literacy training. The needs for literacy training remain important, since functional literacy training targets the poorest women. Each project has prepared literacy textbooks that are compliant with WFP’s basic requirements and adapted to the local conditions. These books should be fully utilized.

## Training participants have improved their educational level and each participant masters in average 2 to 3 practical skills and are ready to be the clients of a micro-credit scheme. FFT activities, i.e. health training, education activities and technical training both to adults and children have a long-term effect on the human capital of beneficiaries.

## WFP has provided PRA training to its counterparts. As understood from fieldwork in Guangxi and Gansu, PRA was introduced with adaptation to food-aid and gender sensitivity and training was provided jointly by WFP staff and national consultants. Some 14 tools such as Community Mapping, Social Network Mapping, Seasonal Calendar, Daily Schedule, Wealth Ranking, Access to and Control Over of Resources/Assets, Problem and Solution Matrix, etc. were selected and adapted to food aid and local circumstance. Country Office prepared PRA booklets in Chinese. However, as experienced in PRA training in Ningxia/Shanxi project, most participants were men with little gender sensitivity.

## Gender Focal Points (GFP) at all levels of PMOs as well as 2-3 female members in VIG have been appointed. The innovative institutionalization of GFPs both in CO as well as at all project levels provides WFP with leverage for implementing the Commitments to Women and addressing gender concerns. The gender sensitization of PMOs staff and appointment of GFPs contributes to further strengthening the process of gender sensitizing mechanisms. In some counties visited in Guangxi, the GFP is from ACWF and acts as Deputy Director of PMO. A Gender Newsletter was issued twice a year both in Chinese and English with contribution from PMOs collecting all interesting beneficiary stories.

## Management and leadership training sessions were offered to women using the UNIFEM module to enable them to participate in the VIG and PMO. However, the mission’s field visits suggest that results from these specific training sessions are below expectations.

## School Feeding was a CP supplementary activity. It aimed at making primary education accessible in poor, remote, minority areas, especially for girls. The target was some 500,000 children from poor families, predominantly girls in rural areas. The activity was subject to the availability of additional food resources. School Feeding was only piloted in Gansu province with assistance to 5,000 girls who received take-home rations to prevent drop-out from primary schools. Such an activity has been appreciated by the beneficiaries and local authority would like to continue even after the project terminates, but no resources have been set a side for this purpose.

## Interviews conducted by the evaluation mission have verified that women are the main labour force in rural society, especially when men have to migrate to find off-farm employment. However, in Guangxi, a PRA showed the increasing trend of agricultural feminization has led to heavy workload for women. It is recommended that time-saving technologies, more women-responsive extension and training services and high-value crops with low labour inputs be promoted to alleviate women’s burden.

## The PRA showed that training in income generating activities need to be better coordinated with other line bureaus and RCCs. Marketing and risk management shall be incorporated in the training to minimize the risks at the lowest possibilities.

## In Gansu, the mission found that a relatively large amount of WFP resources had been used for income generating training purposes, despite the fact that IFAD had not started disbursing loans yet. (when the mission visited Gansu, the project was still preparing the loan negotiations). The PMO staff interviewed by the mission expressed concern that the effectiveness of the training was reduced when not applied immediately. PMO staff indicated to the mission that efforts will be made in getting support from the local government to minimize the loss. It is recommended that training for income generating activities be implemented when micro-credit is available to optimize the combined effects of both interventions.

## For loans related to agricultural and animal raising activities, technical backstopping is considered crucial to help deal with diseases and other risks. Some cases show that women are still not so confident in using the loan. In Longe Village of Guangxi, a woman received a loan of 3,000 Yuan from ACWF to raise 3 pigs. The pigs died three months after and it became the heavy burden for this woman to repay ACWF. ACWF could not be blamed for not offering technical back-up since each ACWF has only 3-5 staff with little capacity for supervision or experience in credit management. Both PMO and ACWF should work out a mechanism for monitoring the women’s credit to keep failure cases to the minimum.

## The RCCs have been selected as the rural financial services delivery system and they are fully responsible for allocation and recovery of loans under the joint project. Given that credit institutions always view poor customers as representing increased risk, RCCs may develop a tendency to shy away from the target groups as their prime customer base, i.e. poor households and women. It is therefore important to establish a mechanism for RCCs and PMOs that makes them able to target the poorest households.

## Efforts were made to provide extension support, literacy and technical training focused on the poorest households, and to support experimental credit delivery mechanisms, from which women in particular, would graduate to commercial credit status.  On-farm trials and demonstrations were conducted on the land of the poorest households, and agricultural inputs were provided to help increase production and reach a higher level of credit worthiness. However, this mechanism needs further development, and the mission found that the cooperation among different stakeholders especially RCCs, PMOs, ACWFs as well as VIGs need to be further strengthened.

F. 	Coordination and Partnerships

## The Project Management Office (PMO) has proved to be an effective and efficient structure for the coordination of project implementation under the overall guidance of Project Leading Groups (PLG). PLGs bring together senior policy-oriented officials present at the various administrative levels to determine the overall and annual project objectives. These commonly include productive investments in food crops, livestock and tree crops, as well as in social sectors such as health and education. Incremental rural infrastructure investments include roads, drinking water and electricity. PMOs generally consist of senior officials detached from their technical units at the respective levels of authority for the duration of the project. Their role is to coordinate and plan the project actions and to monitor and report on progress achieved. Implementation experience shows that the required coordination between the different sectoral agencies is effectively and efficiently ensured with the PMOs.

## The use of PLGs, PMOs and Village Implementation Groups (VIG) is an approach, which has evolved over time. It ensures effective participation and improves timeliness of implementation. The approach has also permitted the introduction of beneficiary participation in planning and selecting project activities. The level of participation of villagers in project planning and implementation was already well established through the use of village committees. The mandatory presentation of Village Development Plans (VDP) for village-level development has further strengthened this process. The reality is that the village chief also tends to lead the VIG of his village. This has the advantage that the hitherto sole elected official in the rural political and economic management structure plays a very important role in project implementation. The participatory qualities of the VIG/VDP system of management are further strengthened by the presence of villages' Women Federation representatives in the VIG. PRA methodologies should be further refined to capture the advantages of the existing structure and to ensure stronger participation by the village poor, the women and the inhabitants of distant "natural" villages or “hamlets”.

## Efforts were made to respond to the recognised need of coordination in external assistance to support the integrated approach to poverty alleviation adopted by the Government. This included coordination of United Nations agency programmes through the UNDAF process, agreements between the China International Centre for Economic and Technical Exchange (CICETE) and UNDP to provide assistance to investment projects supported by IFAD, the World Bank and WFP.

## The ideal synergy between IFAD and WFP has not always been reached for reasons elaborated in a report of WFP/IFAD Partnership in China. Thus, during the on-going CP uncoordinated donor practices have resulted in joint programme with different project areas and different target groups. In Gansu, a number of 22,649 women have received training for income generation activities while IFAD loan is still yet to be approved. PMOs have recognized the problems and indicated that RCC’s would replace, to the extent possible, IFAD loans. However, in the case of Gansu, it was clear enough from the beginning of the CP that IFAD loan was delayed. Local Government or other international organizations such as World Bank should have been approached to replace IFAD in that particular project. It seems that the problems related to synchronisation between the two agencies have been exacerbated since 2001 with the Ningxia/Shanxi Environment Conservation and Poverty Reduction Programme and the above-mentioned Gansu Agricultural Integrated Programme. IFAD project in Ningxia/Shanxi was started two years after the programme was approved and when WFP had almost finished its operation in this area.

## As pointed out in Section 1 of the report, full benefit of the IFAD/WFP partnership can only be obtained with a synchronized approach, where IFAD loans are distributed immediately after FFT activities have been implemented as planned. Joint Government/IFAD/WFP mid-term reviews should have been systematically organized to reformulate some project components according to the availability of resources.

G. 	Resource Utilisation, Budget and Logistics

### Resourcing

## China CP (2001-2005) was approved by the Executive Board in February 2001 for a total cost to WFP of US$86 million. The total tonnage approved was 547,000 mt divided between the basic activity Integrated Rural Development (IRD) and the supplementary activity school feeding as shown below. Unfortunately, no funds were contributed for school feeding until 2004 when TNT donated 107 mt for school feeding in Gansu province. In June WFP China organized a walk the world event and collected US$51,000. Additionally, US$20,000 was collected during a private sector award dinner from HP, Oracle, CNBC, TNT and CBN, and together this will buy 292 mt. The contributions amount to 0.2 percent of the planned resources for the school feeding.

## As of April 2005, the basic activities were funded with 81 percent of the planned resources. This includes the last shipment that arrived in China in 2005. The donors have been mainly Canada (multilateral funds) and Australia (directed multilateral funds). The 19 percent average shortfall over the 5-year period hides high shortfalls for 2003 and 2004, respectively 38 percent and 42 percent. This led to a total cancellation of the activities in Xinjang, which based on VAM indicators were estimated to be the least vulnerable of the selected provinces. Furthermore, it led to shortfalls in all the other provinces causing low implementation rates, especially in 2004 (47 percent).

Resourcing of CP (2001-2005) in mt

|  | IRD | School Feeding | Total Per Year |
| --- | --- | --- | --- |
|  | Plan | Actual | % | Plan | Actual | % | Plan | Actual | % |
| 2001 | 72,770 | 69,149 | 95 | 100,000 | 0 | 0 | 172,770 | 69,149 | 40 |
| 2002 | 78,086 | 77,542 | 99 | 60,000 | 0 | 0 | 138,086 | 77,542 | 56 |
| 2003 | 83,558 | 51,660 | 62 | 40,000 | 0 | 0 | 123,558 | 51,660 | 42 |
| 2004 | 68,684 | 39,893 | 58 | 0 | 1,294 | 0 | 68,684 | 40,293 | 59 |
| 2005 | 43,450 | 43,450 | 100 | 0 | 0 | 0 | 43,450 | 43,450 | 100 |
| Total | 346,548 | 281,694 | 81 | 200,000 | 1,294 | 1 | 546,548 | 282,094 | 52 |

## Provinces have taken different approaches to targeting in the case of shortfall reflecting an on-going discussion of how to manage shortfall in WFP projects all over the world. The distribution numbers indicate that Guizhou, Hunan and Guanxi did not reduce the number of beneficiaries despite not having enough resources to maintain the planned ration size and workdays, thus prioritizing coverage over impact. In Shaanxi/Hubei and Gansu they reduced the beneficiary numbers to avoid having to spread the food and the activities over too many beneficiaries and thus diluting impact. Through interviews with the provincial PMOs visited by the mission it was clear that the PMOs had made these decisions very consciously (but without guidance from the CO); one arguing that however little food is received, is better than nothing, and the other argued that it was more important to maintain the quality of the intervention by maintaining the planned rations and workdays and instead reducing the number of beneficiaries. They chose to keep the number of planned townships and counties and do the de-selection at village and household level.

## By way of example, 46 percent of the planned food was distributed to 93 percent of the planned beneficiaries in the training activities in Guanxi in 2004. The PMO chose to reduce the amount of training days with almost 50 percent to maintain the number of beneficiaries. This was a conscious choice in order to maintain coverage, and ensure that everyone gets a little, rather than a few getting what was planned. In Gansu they did the opposite, reducing the number of beneficiaries in order to make sure that the quality of the length of the training courses was maintained.

## Prompted by the ED’s visit to China in late 2004, where only half of the planned implementation was going on, US$2 million was released from the insurance fund for which the CO could buy wheat locally to restart activities where they had stopped due to the shortfall. Simultaneously, China became one of the Business Process Review pilots. This allowed the CO to borrow 4 million worth of food from the Government to start implementation on time in 2005. The food was returned to the Government when the last WFP shipment arrived in China in April 2005.

### Counterpart Funding

## At design of the CP it was foreseen that the Government of China would provide 510,400 mt of food and US$210 million cash in support of the CP components. It was foreseen that the WFP/GOC ratio would increase from 1:1.5 to reach 1:2 by 2003. Ultimate transfer of ownership of activities and implementation modalities to the Government would take place after 2005, when WFP will phase out of project activities. It was also foreseen that GOC will continue implementation in Gansu 2006 and 2007 with 16,000 mt. The Government covers all landside transport, storage and handling costs (LTSH) and has covered all external transport costs for new activities developed under this CP.

Table 13 - GOC Inputs 2001-2005

| Year | Cash/Commodities | LTSH | Ocean Freight | GCCC | Total |
| --- | --- | --- | --- | --- | --- |
| 2001 | 24,895,958 |  | 859,018 | 48,391 | 25,803,367 |
| 2002 | 34,000,000 |  | 970,580 | 48,391 | 35,018,971 |
| 2003 | 44,929,000 | 3,000,000 | 969,836 | 48,391 | 48,947,227 |
| 2004 | 35,000,000 |  | 1,194,865 | 48,391 | 36,243,256 |
| 2005 |  |  | 1,824,900 | 48,391 | 1,873,291 |
| Total | 138,824,958 | 3,000,000 | 5,819,199 | 241,955 | 147,886,112 |

## Additionally the GOC has assumed the costs of management and implementation for all activities. This entails offices, staff, vehicles, technical supervision, etc. We do not have the costs for this, but it is of course a substantial amount that is not included here. Unfortunately the funds that were planned for continuing the activities in Gansu (16,000 mt) have been used to make up for the lack of IFAD funds for infrastructure works and training. According to the provincial PMO, there will be no more government funds for Gansu after 2005.

### Logistics

## WFP food is delivered at Chinese ports. The State Food Bureau assumes responsibility for discharge, transport, storage and distribution to beneficiaries. WFP wheat is merged with GoC stocks on a ton-per-ton basis. The equivalent amount of GoC wheat is released from warehouses closest to project areas according to instructions issued by the relevant PMO. The food is released to the village leader accompanied by the township or county against a list of beneficiary name and quantity signed by the county PMO. In the areas where rice is the preferred stable food, the quantity of wheat is converted into rice.

    - Monitoring

## A viable monitoring system exists based on comparison of input versus output which has been designed by WFP, monitored by the PMOs at county level and computed at provincial level. Every six months, reports are sent to the CO Beijing and until the end of 2003 they were regularly followed-up by the respective WFP Programme Officers. With the Programme Officers’ departure, however, systematic monitoring has become sporadic, reducing WFP’s ability to follow the implementation and impact of activities.

## The output reporting has been simplified in order to be able to compile various projects into one single matrix of activities as required by the SPR format. Figures have been aggregated and detailed implementation related information lost. The GIS database prepared by the VAM China unit could have been used to provide a geographical visualization of activities, or to assess progress of the various agreed VDPs. Close monitoring of effective progress of individual activities in line with these VDPs, close follow-up of effective work performed under each of these VDP are important information that could have been compiled. As of today, outputs have not been analysed and there was no follow-up.

## The monitoring system was not designed to reflect results at outcome level and impact at household and village community levels, which were the focus of the CP. This concerns particularly the following questions: did the project activities contribute to fill the food gap and, to which extent, did households gain and preserve assets? Did the different types of training effectively result in an improved capacity and knowledge of the beneficiaries? Did the village community acquire better sanitation, transportation and agriculture production conditions? The introduction of a qualitative monitoring system of project activities in a selected number of villages could have supported the follow-up and management of the projects. Such impact monitoring would have required the implementation of baseline surveys in each province. Some provinces - e.g. Guangxi - have carried out a baseline survey based on IFAD requirements, design and training.

## IFAD has, in recent years, developed a Result and Impacts Management System (RIMS) to be added into the existing M&E system to measure outcome and impacts of the project   with reference to a project logframe. All on-going projects are requested to conduct three-round surveys on household economy to measure the outcome of the project interventions. To date, the baseline surveys in Shaanxi, Hubei and Guangxi have been finished and benchmarks for future comparison have been established.

## An integrated M&E between IFAD, WFP and GOC does not exist. Each partner has its own requirement for monitoring its share of the programme and PMO reported consequently. A global monitoring of the whole project, including the expected interactions and synergies expected from the inputs of different partners, would have provided a more realistic picture of the actual impact of the projects and permitted to assess the validity and efficiency of the original partnership concept. A fully fledged M&E system would have required financial and human resources that WFP Country Office did not have during the phasing out phase.

I.	Phasing out

## According to the plan the CO will end project activities by December 2005, but WFP will keep a small office to maintain relations with the Government of China. At the time of writing the exact role of WFP’s office in China was still being discussed. In the design of the CP there was a commitment to monitor the phase out, counterpart capacity building in VAM and disaster management. As the implementation developed this was not found to be relevant by the CO, and consequently not pursued. However, the PMOs mentioned that they had strengthened their ability to target HH through wealth ranking and other PRA type methods, and to systematize the monitoring of the project outputs and outcomes. The mission considers this an important contribution by WFP.

## When the CP started in 2001, the CO had 21 national staff and 9 international. By December 2003 there were only 4 international staff left. The last programme officer left in February 2004. Fortunately the CO has been able to benefit from secondments of very capable staff from provincial PMOs and from bilateral donor agreements. Unfortunately there was no handover of responsibilities from the leaving programme officers to this new staff. The mission sees the effect in the follow-up of the projects that are still on-going and in fact picking up implementation after the last contribution that fully funded the operation for 2005.  The mission recommends that in time of transition more attention is given to a responsible phase out of project activities. It is necessary that a minimum of staff is present to follow-up on activities and ensure that they are finalized according to the plan. If the operations are poorly funded, which is often the case when phasing out, special funds should be released from HQ.

## The relevance of beginning new initiatives (BPR, walk the world, school feeding) so late in the programme could be questioned; especially considering that there are many extra tasks to perform when phasing out or transforming the typology of the office like in China, and the staff was downsized so quickly. The new initiatives have of course required some extra staff time, which could have perhaps been spent more wisely on the projects already in place and on the recording of the phase out. The sustainability of starting the school feeding programme so late is also questionable seeing that there is no intention of the Government of China to continue the programme after December 2005.

J.	Conclusions on CP Evaluation

## Beneficiary participation in the implementation of the CP’s basic activities has been massive and active. The utilisation of a participatory process in project preparation, planning and implementation is unanimously acclaimed by beneficiaries and technicians at different levels. The process adopted through creation of Village Implementation Groups and elaboration of Village Development Plans (VDP) by the village communities has empowered the village population and design project activities which better match the actual needs of the villagers.

## Land development and infrastructure construction had a major impact on household long term food security through increased grain yields, estimated at least at 30 percent by the farmers. CP activities have helped to alleviate women’s traditional workload (water, straw or wood fetching and grain processing) and create new opportunities for income generation activities. However, women’s increasing participation in agricultural activities comes in addition to their traditional activities, resulting in heavier workloads.

## Training of trainers in literacy and agriculture, demonstration plots for agricultural techniques, as well as training of mid-wives and health attendants in each project village has provided a solid basis for further capacity building. For technical skills training, the actual 4 to 5 days delivered (versus 10 days planned) is not be sufficient for farmers to gain solid and sustainable knowledge.

## For land, water and natural resource components, while overall achievements are remarkable, impact on the overall natural resource base has been somewhat diluted by an attempt to encompass as many beneficiaries as possible with limited resources. Designing a more comprehensive micro-shed plan with the communities living in small hamlets could have encompassed a series of wider community works that benefit all inhabitants of the hamlet or micro-shed to better address overall sustainability. Resources allocated to the social infrastructure activity were however not sufficient to cover the needs of all the village households. Comprehensive village sanitary development could not be achieved with the resources allocated within the activity.

## The Government has continued to show a strong commitment to WFP’s development projects and increased its contribution. IFAD/WFP partnership has enabled the successful integration of education, training, health and credit components making a significant impact on the improvement of rural livelihood. However, problems of activity synchronization were encountered with delayed Government approval of IFAD loans and joint Government/IFAD/WFP mid-term reviews should have been systematically organized to reformulate some project components according to the availability of resources.

## The programme approach adopted by WFP intended to move away from individual projects. However, as pointed out by the evaluation of “Enabling Development Policy” the China CP like a number of “Country Programmes approved by WFP Executive Board, consist of a number of specific Projects, called Activities, within a Country for a set period, normally five years, to achieve a common goal". Whereas in the previous project approach each project was submitted to some form of appraisal and was to include its own monitoring and evaluation, the programme approach has oversimplified “project or activity” preparation and monitoring to one single overall appraisal conducted before EB's approval of the programme.

## The design of the China’s CP was based on the assumption that the IFAD-WFP partnership will enable WFP to consider that the appraisal work conducted through IFAD according to its own procedures could be used as a shared baseline within which WFP could insert and define its own contribution. Limited use was done from IFAD technical studies and as the result the Programme design has been less site specific or sector specific than in the past with the consequence that previous design and planning of activities have just been translated into a list of individual assets and activities losing the integrated geographical or watershed approach.

- Lessons Learned

- FFW have had an important and lasting impact on household food security notably through works related to dry land improvement and irrigation schemes. The steady increase in productivity and better farmer incomes provided a basis for further diversification of activities, social infrastructure development and access to off-farm income. FFT is essential for human capacity building but cannot reach its full benefit as a stand-alone activity. Literacy and basic health and nutrition training had an important impact on empowerment of the poor, especially women. Training requires a long-term sustained effort, which should continue after project completion.

- Better results are gained by an increased involvement of beneficiaries in the project life cycle (design and implementation) through the utilization of PRA methods in WFP project preparation, planning and monitoring have been successfully introduced in China. A better beneficiary participation has permitted to match the actual needs of the villagers, empowering the village population through the creation of Village Implementation Groups and elaboration of Village Development Plans, and inducing further commitment of beneficiaries. Increased consideration for the role of women and their participation in project activities proved to be essential. Various factors external to the projects have contributed to their successful implementation: availability of markets, access to credit and non-food inputs, agricultural extension and high government commitment at all levels.

- Coordinated Government action is a pre-requisite to a successful integrated approach to poverty alleviation. The creation of the Leading Group on Economic Development of Poor Areas appointed by the State Council has been a significant step forward. It was followed by the support and commitment of Government authorities at all levels which led to cooperation between different technical bodies. The Project Management Office structure has clearly demonstrated a successful integration of different Government ministries for the implementation of multi-sectoral development projects.

- Project formulation, technical reviews and evaluation missions are key instruments for proper project implementation and corporate learning. A systematic organization of technical reviews and evaluations is needed during project implementation in order to adapt the operational plans to changing needs or new technical requirements that may emerge during implementation. Technical assistance and supervision is essential to the achievement of the desired results. More attention should be given to maintenance and access to technical knowledge. The relative decreased of in-depth appraisals and mid-term reviews during the last decade – and especially during current CP implementation - have indeed demonstrated the usefulness and necessity of such exercises to adapt strategies and activities during project implementation.

- When limited resources are spread out the required synergy is insufficient between project activities. Multiply interventions in a great number of communities to reach a larger number of beneficiaries do not result in a sustainable impact. On the other hand, comprehensive watershed management or sound village sanitary development involving long-term planning by the village communities proved to be an efficient approach to sustainable development.

- The value added given by the cooperation between different UN agencies, international institutions, bilateral cooperation, and other organizations are instrumental to successful programmes. However, systematic appraisal and monitoring of all activities undertaken in common by all partners are necessary. Furthermore, when more than one international institution is involved in the implementation, more attention needs to be paid to coordination to ensure adequate timing of the inputs and harmonized reporting requirements.

- Particular attention should be paid to ensuring a proper phasing out for a WFP Country Office entering into an exit strategy phase of development activities. It appears necessary that a minimum of professional staff be present to follow up on activities and that a proper level of resources – both in commodities and in staffing – be guaranteed since it is even more crucial at the phasing out stage to ensure sustainability and to capitalize on the experience gained.

- Committed Government action is a pre-requisite to a successful integrated approach to poverty alleviation. The creation of the Leading Group on Economic Development of Poor Areas appointed by the State Council has been a significant step forward. It was followed by the support and commitment of Government authorities at all levels which led to cooperation between different technical bodies. The Project Management Office structure has demonstrated a successful integration of different Government ministries for the implementation of multisectoral development projects enhancing the IRD approach. The model for progressively increasing counterpart funding, the funding of the implementing structures (PMO model) and Government cost sharing of the Ocean freight and all landside transport should be explored for replication in other countries with similar capacity.

Annexes

Annex 1 – Terms of Reference for the Evaluation of WFP Operations in China

a)	Background

WFP has been present in China for 25 years (since late 1979) and during this period has committed almost a billion US dollars of assistance under 68 operations, comprised of 53 development projects, 11 development quick action projects, 3 emergency operations and one (on-going) Country Programme. Two of the last stand-alone development projects have been subsumed into the current Country Programme.

The focus of WFP’s operations in China has been on development, with approx. 90 percent of commitments being for development and 10 percent for emergencies. There have been no PROs or PRROs in China. Of the three EMOPs approved for China over the 25 year period, two (in 1979 and 1981) were modest in size, while the last one (EMOP 6045, for flood affected people) was large, with an approved budget of over US$93 million.

According to a note prepared by WFP/Beijing, there have been three main phases of programming in China, as follows:

- 1979-1981: Reconstruction assistance to Indo-Chinese refugees (continuing to 1984).

- 1982- 1990: Sectoral development (forestry fisheries and dairy).

- 1990-present: Integrated rural development projects with a focus on people, food security and poverty alleviation.

In the early 1990s WFP began shifting its support from an Integrated Agricultural Development (IAD) approach, focusing mainly on measures to increase food availability and income for the poor, to an Integrated Rural Development (IRD) approach. The IRD model, in addition to meeting the food needs of the poor, also addresses human capital formation. The increasing recognition by the Government that achieving more effective and sustainable poverty reduction requires integrated interventions led to the decision in 1996 by the Ministry of Agriculture (MOA), WFP and IFAD to establish a joint programme partnership. The MOA has been WFP’s main operational partner in China.

Throughout the history of WFP’s presence in China, the relationship with the host government has been of primary importance and the government has played a key role in project execution.

After some 20 years of stand-alone projects, WFP introduced the Country Programme approach in China in 2001, with a five year CP running from 2001 to 2005. A phasing-out framework for WFP assistance to China had been discussed at the Executive Board’s first regular session of 2000 and a Country Strategy Outline (CSO) had been endorsed at the third regular session of the same year. In the latter document it was foreseen that WFP assistance would be decreased over a five-year period, moving towards the phasing out of WFP assistance by the end of 2005. This plan is currently on track. Although WFP will close the main Country Office at end 2005, a Liaison Office will be left in Beijing, inter alia to provide support to WFP operations in DPR Korea and to facilitate dialogue with the Chinese authorities on issues such as advocacy and fund-raising.

In terms of resources, WFP operations have been based, for the major part, on an arrangement whereby imported wheat is exchanged for local wheat released at the provincial level of the project locations. This arrangement has saved on ITSH costs. Lesser amounts of other commodities have been supplied, however, over the years (rice, canned fish, edible fat, lyophilized beef). Over the 25 years period from 1979 to 2003 a total of 3,356,461 tons of commodities have been delivered by WFP to China (mostly wheat). Deliveries peaked during the five years period from 1984 to 1988 when they totaled some 1.6 million tons, or 48 percent of all deliveries during the 25 years period. Some of the 1987/88 deliveries were pre-shipments for the immediate following years, however.

Following the global trend of a decline in WFP development resources, which started in the 1989-90 period (due to resources demand pressure from new large-scale emergency operations and PROs/PRROs) deliveries to China in recent years have been significantly lower than the peak years of 1984-88. For example, total development programme deliveries during the past five year period were less than 25 percent of the deliveries of the peak five year period of the mid-late ‘80s.

To give an idea of the current level of WFP assistance, it may be useful to note that, in 2002, WFP provided food aid to 1.86 million people (approx. 0.15 percent of China’s population at that time of 1.26 billion). WFP was working in 60 poverty-stricken counties of eleven central and western provinces of China. Assistance amounted to 74,922 metric tons of wheat and 1,834 tons of rice, valued at US$10.5 million. The donors were Canada (61 percent) and Australia (39 percent). In 2003, donations totaled 51,660 tons. Since 2001 the China programme has faced increasing shortfalls against its requirements and these were of the order of 35 percent in 2003. The 2004 situation was again problematic and had an impact on programme implementation.

The Office of Evaluation (OEDE) has evaluated the China operations at regular intervals over the years. A list of evaluations will be found in the draft bibliography attached to these TORs. The last significant development evaluation was the “Ex-post evaluation of the impact and sustainability of selected WFP-assisted projects in China”, the summary report of which was presented to the EB in March 1997. An evaluation of the large flood EMOP, # 6045, (which provided assistance in the period from October 1998 to March 1999) took place in late 1999. The Country Programme has not yet been evaluated.

b)	Purpose and Scope of the Evaluation

In consultation with the Regional Bureau in Bangkok (ODB) and the Country Office, the Office of Evaluation put an evaluation of the China programme on its evaluation work plan for 2004-05. The Executive Board approved the OEDE work plan at its third regular session in October 2003 (annex III to the Biennial Management Plan). The intention was to undertake a final evaluation of WFP operations in China before the closure of the Country Office at the end of 2005, particularly with a view to capturing any lessons which may be of corporate interest and use.

The main objectives of the evaluation are to:

- Review and record the main elements of WFP’s 25 years of assistance to China in a succinct manner.

- Evaluate WFP’s current Country Programme, with a focus on activity outcomes and impact.

- Capture lessons which may be of wider corporate interest, as part of WFP’s broader learning initiative.

Thus, the overall exercise may be seen as being comprised of two stages.

The review will focus on the first 20 years (1979-1999) of WFP’s assistance to China and will involve considerable document research, basing on approved project documents, progress reports, completion reports, evaluation reports etc. This will be primarily a desk study (which may be supplemented by face-to-face and telephone interviews with WFP staff involved in the China operation in earlier years, to the extent that they are available) and will be undertaken primarily in Rome, prior to the mission’s travel to China. The review will provide a background setting for the subsequent field work and evaluation of the on-going Country Programme. The focus will be on WFP’s development projects (90 percent of all resources delivered), although documentation on the major emergency operation of 1998-99, including the OEDE evaluation reports, will also be reviewed. A draft review document should be available before the mission travels to China, but may be up-dated while in China, from additional information available in-country.

The evaluation of the on-going Country Programme (2000-2005) will take up most of the mission’s time while in China and will seek to establish what outcomes and impact WFP’s recent development interventions have had.

c)	Key Issues for the CP Evaluation

The evaluation team will examine the following issues in connection with the Country Programme. The list is comprehensive and the team leader and team members may decide upon a prioritization of the key issues before the start of the mission, in consultation with the Country Office. This may lead to a rationalization of the overall list, keeping in consideration the time available for the evaluation mission and the need for realism about what can be covered in the time available to the mission.

- Strategy

- Is the CP strategy consistent with WFP’s core mandate, the Enabling Development policy and the Enhanced Commitments to Women?

- Is the CP consistent with the priorities set out in the UN system’s Common Country Assessment (CCA) and UN Development Assistance Framework (UNDAF) processes?

- How was the transition from stand-alone projects to the CP managed?

- Were other agencies involved in the initial problem analysis?

- Did the preparation process adequately involve beneficiaries (both men and women)?

- Were constraints to implementation adequately addressed at the outset?

- How would the CP and its component activities be designed and managed differently, if the same CP and its activities were to be re-started now?

- Was an exit strategy developed?

- Design

- Were objectives set at the right level (i.e. in compliance with logframe definitions) and were sound means-to-end linkages made between inputs, activities, outputs, outcomes and impact?

- Achievement of Objectives

- To what extent have planned outputs been achieved in terms of quantity, quality and timeliness?

- Are resources being effectively and efficiently used?  Is food aid the most appropriate resource?

- What evidence is there that the CP’s stated purpose(s) and goal were achieved?

- Targeting

- How were beneficiary areas and groups identified?

- Are targeting objectives appropriate?

- Are arrangements made to review and up-date the targeting strategy?

- Are male and female beneficiaries involved in the negotiation of beneficiary status?

- What is the proportion of male and female beneficiaries participating in Food-for-Work (FFW) and Food-for-Training (FFT)?

- Appropriateness of Rations

- Is the food ration adequate and appropriate vis-à-vis the livelihood and coping strategies of both men and women?

- Implementation

- Are plans being followed?  If not, why not?

- Did objectives change during implementation? Why? On the basis of what analysis or what events?

- Have there been delays in implementation? How have these been dealt with? What was the impact of such delays? To what extent are these delays due to internal difficulties and to what extent to WFP resources shortfalls or other external constraints?

- Monitoring and Reporting

- Were baseline data collected and were appropriate indicators identified at the outset for measuring progress and results?

- Do the monitoring systems work, including the extent to which gender considerations are built into monitoring arrangements?

- What is the type and frequency of reporting for the CP, including periodic participatory appraisals, in any? Have reports been submitted on time? Are they complete? What problems have been experienced? Is the information analyzed and used to make decisions on the management of the CP?

- Coordination, Partnerships and Beneficiary Participation

- What mechanisms were put in place for coordination with the Government, donors, UN agencies etc. and how effective were they? Are sector responsibilities successfully divided among partners?

- How are the provincial Project Management Offices (PMOs) organized and are they effective?

- Are implementing partners fulfilling their obligations? What training of partners has taken place? What capacity will be left behind?

- In what way have the beneficiaries participated in the design, implementation and monitoring of the operation? Were the arrangements adequate? What was the impact of their participation or non-participation?

- How is the special partnership with IFAD functioning – its development, nature and actual functioning? What problems and constraints have been encountered? What is the value added? What lessons may there be for WFP-IFAD cooperation and development interventions in other countries?

- Commodity Control and Logistics

- How has the imported wheat for local wheat exchange arrangement worked? On what basis is the exchange made (ratio)? How has WFP/Beijing tracked deliveries and distributions to beneficiaries? Have there been any significant losses in recent years?

- Was planning for logistics, transport, storage, staffing and national auditing adequate?

- Budget and Resources

- What percentage of foreseen resources under the CP has been delivered against the target for the said period (i.e. by March 2005)?  What are the reasons for the shortfall? How have any shortfalls been managed? What have been the consequences of any shortfall for CP activity implementation?

- How predictably and regularly have resources been supplied to the CP?

- Was the WFP operational budget appropriate in relation to the objectives/activities, and what factors affected individual budget items, particularly direct support costs?

- How successfully has the CP resourced its non-food item (NFI) requirements, if any, and what have been the constraints?

- How has the planned WFP/government cost-sharing under the CP worked in practice?

- Outcome/impact and Sustainability

- What difference did the project make to the lives of the beneficiaries (nutritional status, livelihood improvements etc.)? Who benefited? If possible, compare to non-project beneficiaries in the same area (i.e. what would have happened if no assistance had been given?).

- How do beneficiaries and other stakeholders value the operation?

- What impact did the project have on household food security and self-reliance?

- What unexpected outcomes (positive or negative) have there been?

- What are the prospects for sustainability of activities and outputs after the end of the CP activities? What factors are likely to undermine the sustainability of benefits?

- What actions are being taken or will have to be taken by WFP, the government, implementing partners and beneficiaries to ensure sustainability of the outcomes of the CP activities?

- What lessons may be learned from the phase-out process?

- Commitments to Women

- To what extent are WFP’s Enhanced Commitments to Women being met it terms of (i) food access by women; (ii) access to power structures and decision-making; and (iii) access to resources, employment, markets and trade?

- What gender training has taken place, for whom, and what difference, if any, has such training made?

- Is adequate effort being made to mainstream as well as advocate gender considerations?

d)	Methodology

As noted above, the preliminary review of WFP’s assistance to China for the twenty years period from 1979 to 1999 will be based primarily on a document research (desk study) in Rome, conducted prior to the mission’s start. It is anticipated that the team leader will take the lead in this exercise, supported by a Research Assistant, as necessary.

The evaluation team leader will assist in finalization of the current draft Terms of Reference, in consultation with the OEDE evaluation manager, the other team members and the Country Office.

The team leader will also take the lead in pre-mission document review pertaining to the on-going Country Programme, including, but not limited to, the following documents. This will result in a brief pre-mission inception report (not more than 15 pages) that captures the most salient details from these documents. A timeline of important events in connection with the CP may be created.

- The UN Common Country Assessment.

- The UNDAF document.

- The World Bank Country Study – China, Overcoming Rural Poverty.

- WFP’s corporate policy documents for Enabling Development (1999), Enhanced Commitments to Women (2002) and new Strategic Priorities (2003).

- WFP’s thematic evaluations of the Country Programme Approach (2002) and Commitments to Women (2002), as well as the China Country Case Study for the latter (see footnote 3, above).

- WFP’s China Country Strategy Outline (CSO).

- The WFP China Country Programme document.

- Individual CP activity agreements.

- Salient extracts from UNOPS Supervision Reports prepared on behalf of IFAD and WFP on the different CP activities (year 2001 onwards only).

- The November 2001 evaluation of WFP-IFAD collaboration in China.

(Other team members will be expected to read all or most of these documents prior to the start of the mission).

While the above documents will be read prior to the mission’s visit to China, it is expected that more specific WFP and implementing partner monitoring and progress reports will be reviewed (from Country Office files) when in Beijing. This will include the full versions of recent UNOPS Supervision Reports on IFAD-WFP interventions (i.e. reports from the start of the Country Programme in 2001 onwards).

The review of documentation for the CP evaluation will be supplemented by the in-country collection, tabulation and analysis of data, in particular related to resources flows, shipments, beneficiary numbers, outputs etc.

Key information interviews of WFP staff, Ministry of Agriculture and other government counterpart staff, implementing partners and beneficiaries will be conducted in Beijing and during field visits. A participatory approach will be adopted in the rural areas, to obtain the views of beneficiaries. It is anticipated that the mission will visit two of the most important of the nine provinces where WFP CP activities are being implemented. The two provinces will be selected on the basis of their ability to highlight issues common to the overall CP. Field visits will be undertaken to project sites, where beneficiary interviews will be conducted. To the extent feasible, interviews with non-beneficiaries should also be arranged, to compare the livelihoods of beneficiaries of WFP CP activities with those on non-beneficiaries.

e)	Team Composition

The team will be comprised of four persons, as follows:

- Team Leader (FAO Investment Centre staff member).

The team leader should be a specialist in rural development, with knowledge of China and food aid, as well as evaluation experience.  Besides undertaking the historical review, the preliminary pre-mission CP document review and writing an inception report for the CP evaluation, the team leader will focus on keys issues nos. 1 (Strategy), 2 (Design), 3 (Achievement of Objectives) and 4 (Targeting).

- Team member (FAO investment centre/staff member or consultant).

The external team member will be specialized in agricultural economics, rural sociology or a similar discipline. He/she should also have experience of participation in evaluations and understand evaluation methodologies. He/she will focus on key issues nos. 6 (Implementation), 8 (coordination, partnerships and beneficiary participation) and 11 (Outcome, impact and sustainability).

- Team member (OEDE staff member – Evaluation Officer).

The OEDE team member is also the mission manager, but will report to the team leader during the mission in his/her role as a team member. He/she will focus on key issues nos. 5 (Appropriateness of rations), 9 (Commodity control and logistics), 7 (Monitoring and Reporting) and 10 (Budget and resources). In addition he/she will examine more specific WFP management issues, including arrangements for the phase-out of the WFP Country Office in China.

- Team member, national consultant.

The national team member should be familiar with development issues in China and with the status of women in rural areas of China. If possible, he/she should also be familiar with food aid programmes. He/she will focus on key issue 12 – Commitments to Women. To ensure gender balance in the team, recruitment of a Chinese female consultant may be preferred.

f)	Schedule

The following is the tentative schedule for the evaluation and the field mission:

| Review/finalize TORs | February 2005. |
| --- | --- |
| Desk review | February-March 2005. |
| Briefing at WFP Rome | First week of April (one day) |
| Travel from Rome to China | Saturday 9 April 2005; arrive Beijing Sunday 10 April 2005. |
| In country mission | Monday 11 April to Saturday 30 April 2005 inclusive. |
| De-briefing of Regional Office | Monday 2 May 2005. |
| Travel to Rome | Monday 2 May evening; arrive Rome Tuesday 3 May morning. |
| De-briefing at WFP Rome | Friday 6 May 2005 (team leader and evaluation manager). |
| Deadline for full evaluation report | 31 May 2005. |
| Deadline for summary report and RTM | 30 June 2005; PEBC editing deadline for EB/2 – 2005 in November 2005 is 26 August 2005. |

It is anticipated that, during the mission to China, the initial five working days (Monday to Friday) will be spent in Beijing, followed by approx. eleven days in two of the provinces. The final three or four days will be spent in Beijing for final meetings, drafting of the Aide-Memoire and a de-briefing with the Country Office and government counterparts.

On current plans, the evaluation summary report and recommendations tracking matrix (RTM) will be presented to EB2 in November 2005.

g)	Products of the Evaluation

The following will be the main products of the evaluation:

- An Aide-Memoire to be used during the de-briefings at the Country Office/counterpart level, Regional Bureau and Rome. This may be supplemented by a Powerpoint presentation, if deemed useful (Aide-Memoire: maximum 7 pages).

- A full (technical) report. This will be the main report of the mission and may contain a number of annexes. (approx. 50 pages for the core report, plus annexes). The historical review document will be incorporated into the full report as an integral part of the main text. The pre-mission inception report, focusing on the current CP, may be included as an annex, if deemed useful.

- An Executive Board Summary Report (max. 5000 words) and a Recommendations Tracking Matrix (max. 2,000 words, with the management responses).

It is anticipated that the full report will provide space for significant sections on the first 20 years of WFP’s assistance to China (i.e. the review), as well as space for the CP evaluation. The EB summary report is likely to give relatively more space to the CP evaluation and more recent developments related to WFP activities in China, including the relationship with IFAD and the phase-out.

Annex 2 – Allocation of Resources (1979-2005)

a) Planned Contributions to WFP-assisted Projects (1979-2005)

| WFP | IFAD | GOVT. OF CHINA | TOTAL |
| --- | --- | --- | --- |
| Total Cost (US$) | % | Total Cost (US$) | % | Total Cost (US$) | % | (US$) |
| 999,967,000 | 43.2 | 168,264,000 | 6.4 | 1,163,991,000 | 50.4 | 2,312,220,000 |

b) Planned Allocation of WFP Resources per Phase (1979-2005)

c) Planned Allocation of WFP Resources per Activity (1979-2005)

Annex 3 - WFP Projects per Sector/Activity (1979-2001)

| WFP Project Number | Project Title | Approval Date | Total WFP Project Budget (US$) |
| --- | --- | --- | --- |
|  | Emergency and Quick Action |  |  |
| 1196EM | Emergence food assistance to Cetovietnames refugees in China | 19/09/1979 | 6,218,852 |
| 2528QX | Farm development and resettlement and rehabilitation of refugees through extension of Nanhai tea plantation | 15/02/1980 | 2,436,654 |
| 2529QX | Farm development and resettlement and rehabilitation of refugees through extension of oil palm production at Nanbin farm | 15/02/1980 | 2,034,997 |
| 2531QX | Farm development and resettlement and rehabilitation of refugees through construction of reservoir and associated works at Gan Zhuang farm | 15/02/1980 | 1,825,550 |
| 2563 | Farm development through sugar cane and tea production in Xinxing farm | 20/05/1981 | 4,382,964 |
| 2565 | Tidal land reclamation in Jiangjian farm | 20/05/1981 | 3,676,160 |
| 2571 | Tidal land reclamation in Pinghsa farm | 20/05/1981 | 3,875,694 |
| 2572 | Construction of reservoirs and ponds and reclamation of wasteland in Binchuan farm | 20/05/1981 | 3,316,444 |
| 1249RF | Food Aid to the people affect by natural disaster | 28/05/1981 | 2,653,444 |
| 2617QX | Flood control project in Jiu Heyuan seed farm | 18/08/1981 | 1,512,825 |
| 2619QX | Farm development and the resettlement and rehabilitation of refugees through the construction of Chen. Reservoir and power station in Xinglong farm | 25/09/1981 | 2,246,343 |
| 3789 | Reconstruction and rehabilitation of infrastructure destroyed or damaged by flash-floods and typhoon | 09/06/1988 | 1,702,700 |
| 4483 | Repair and reinforcement of fish-ponds and construction of houses destroyed by typhoons | 19/09/1990 | 936,350 |
| 6045 | Emergency Food Aid to Flood-affected People | 18/09/1998 | 93,351,254 |
|  |  | Total | 130,170,231 |
|  | Sectoral Assistance |  |  |
| 2605 | Erosion control and development through forestry and pasture | 29/10/1981 | 22,817,703 |
| 2604 | Command area development | 29/10/1981 | 8,494,700 |
| 2672QX | Agricultural development through drainage, irrigation and salinity control | 11/07/1982 | 1,674,800 |
| 2606 | Land protection and wood production through forestry development | 29/04/1982 | 12,750,000 |
| 2633 | Development of fishery resources | 29/04/1982 | 10,385,800 |
| 2639 | Xingpuzichuan irrigation project | 15/10/1982 | 10,373,457 |
| 2643 | Nan Shan Tai irrigation project | 15/10/1982 | 7,607,200 |
| 267201 | Agricultural development through drainage, irrigation and salinity control | 27/05/1983 | 7,870,000 |
| 2647 | Dairy Development | 27/05/1983 | 77,098,424 |
| 2673 | Agriculture development through warping and improved drainage and irrigation | 28/10/1983 | 14,866,624 |
| 2677 | Agriculture development through improved drainage and irrigation | 28/10/1983 | 9,150,000 |
| 2758QX | Development and protection of Wolong nature reserve | 31/05/1984 | 887,000 |
| 2700 | Development of aquaculture in low-lying saline-alkaline areas | 31/05/1984 | 11,798,103 |
| 2719 | Command Area Development | 11/06/1984 | 15,166,494 |
| 260401 | Command Area Development | 06/08/1984 | 8,652,245 |
| 2697 | Irrigation Project | 06/08/1984 | 15,951,371 |
| 2698 | Irrigation Project | 06/08/1984 | 18,750,577 |
| 2696 | Improvement of camellia tea-oil plantations | 06/08/1984 | 15,412,069 |
| 2730 | Development of fish and forage production in low-lying, saline-alkaline areas | 06/08/1984 | 13,775,064 |
| 2699 | Rural roads construction for developing mountainous areas | 06/08/1984 | 8,657,524 |
| 2708 | Improvement through irrigation of low-yielding lands | 11/09/1984 | 21,019,036 |
| 260601 | Land protection and wood production through forestry development | 10/03/1985 | 16,286,275 |
| 2772 | Erosion control | 10/03/1985 | 16,184,183 |
| 2771 | Development of coastal aquaculture | 10/03/1985 | 21,981,646 |
| 2744 | Improved land use of Loess Plateau | 31/05/1985 | 11,392,154 |
| 2749 | Rural water supplies | 31/05/1985 | 16,952,683 |
| 2811 | Establishment of forests | 06/05/1986 | 13,226,745 |
| 2799 | Development of aquaculture in low-lying areas | 30/05/1986 | 9,814,542 |
| 2814 | Development of integrated fish farming | 29/10/1986 | 42,178,596 |
| 2817 | Development of feed production | 06/02/1987 | 21,780,963 |
| 3364 | Reconstruction of housing destroyed or seriously damaged by fire | 25/05/1987 | 1,772,700 |
| 3146 | Improvement of low lands | 28/10/1987 | 17,911,296 |
| 3356 | Erosion control through forestry and other means | 06/09/1988 | 17,738,005 |
| 3225 | Integrated Development | 06/09/1988 | 10,358,564 |
| 3557 | Agricultural Development through irrigation | 12/12/1988 | 6,180,286 |
| 3357 | Agricultural Development | 12/12/1988 | 4,361,267 |
| 3355 | Agricultural Development through irrigation | 06/01/1989 | 18,600,226 |
| 4047 | Rehabilitation of forests and infrastructure damaged by natural disaster | 05/08/1989 | 1,873,198 |
| 3730 | Agricultural Development | 06/07/1990 | 20,170,124 |
| 3737 | Integrated Agricultural Development Project | 14/12/1990 | 13,044,179 |
| 3779 | Rural Infrastructure | 14/12/1990 | 26,012,673 |
|  |  | Total | 620,978,496 |
|  | Integrated Agricultural Development |  |  |
| 3893 | Integrated Agricultural Development Project | 27/05/1991 | 15,584,875 |
| 3923 | Soil and Water Conservation | 13/12/1991 | 11,083,693 |
| 3924 | Agriculture and Infrastructure Development Project | 29/05/1992 | 16,315,167 |
| 4071 | Poverty Alleviation and Environmental Rehabilitation | 06/04/1993 | 15,350,194 |
| 4355 | Integrated Development of low-yielding land | 26/05/1994 | 17,127,601 |
| 5181 | Integrated Agricultural Development Project | 26/05/1995 | 16,270,528 |
| 5652 | Integrated Agricultural Development Project | 24/05/1996 | 18,897,697 |
|  |  | Total | 110,629,755 |
|  | Integrated Rural Development |  |  |
| 5717 | Integrated Agricultural Development Project | 25/03/1997 | 12,907,626 |
| 5796 | Integrated Agricultural Development Project | 24/12/1997 | 3,329,418 |
| 6023 | Minorities Integrated Agricultural and Social Development Project | 07/07/1999 | 2,989,875 |
| 6147 | Poverty Alleviation Project | 02/09/2000 | 13,054,181 |
| 6166 | Rural Development Project | 24/12/1999 | 6,500,000 |
| 10055 | Country Programme Integrated Rural Development and School Feeding | 14/02/2001 | 99,407,150 |
|  |  | Total | 138,188,250 |
|  |  | Total Global | 999,966,732 |

|  | Workdays |  | mt |
| --- | --- | --- | --- |
| Total in all projects | 1,165,262,644 |  | 3,787,103.59 |
| NB: Number of MT is calculated based on a standard work norm of 3.25 kg (wheat) per workday. |

Annex 4 - WFP Food Allocation per Sector/Activity (1979-2005)

| Activity | Work Days | % of the | mt per |
| --- | --- | --- | --- |
|  |  | Work Days | Activity |
| Emergency and Quick Action |  |  |  |
| Infrastructure | 4,518,223 | 0.39 | 14,684.22 |
| Miscellaneous | 998,000 | 0.09 | 3,243.50 |
| other | 46,500 | 0.00 | 151.13 |
| Total: | 5,562,723 | 0.48 | 18,078.85 |
| NB: This sector has approximately 300,000 mt of free food distribution without indication of activities |
| Dryland Development - Soil and Water Conservation |
| (including approximately 82,000 hectares of terracing) |
| Dams | 14,762,800 | 1.27 | 47,979.10 |
| Dikes | 6,874,500 | 0.59 | 22,342.13 |
| Ditches | 500,750 | 0.04 | 1,627.44 |
| Dryland improvement | 64,582,596 | 5.54 | 209,893.44 |
| Gully correction | 222,781 | 0.02 | 724.04 |
| Infrastructure | 11,790,099 | 1.01 | 38,317.82 |
| Miscellaneous | 846,153 | 0.07 | 2,750.00 |
| Other | 29,430,462 | 2.53 | 95,649.00 |
| Pasture development | 4,387,960 | 0.38 | 14,260.87 |
| Plantation fodder | 7,780,875 | 0.67 | 25,287.84 |
| Soil deepening | 3,022,800 | 0.26 | 9,824.10 |
| Terracing | 60,819,396 | 5.22 | 197,663.04 |
| Water and soil conservation works | 12,369,048 | 1.06 | 40,199.41 |
| Total | 217,390,220 | 18.66 | 706,518.22 |
| Irrigation and Drainage (including approximately 400,000 hectares of irrigated land) |
| Canals | 47,626,741 | 4.09 | 154,786.91 |
| Ditches | 10,415,924 | 0.89 | 33,851.75 |
| Drainage system | 69,631,277 | 5.98 | 226,301.65 |
| Infrastructure | 5,084,080 | 0.44 | 16,523.26 |
| Irrigation system | 59,590,467 | 5.11 | 193,669.02 |
| Land levelling | 112,482,907 | 9.65 | 365,569.45 |
| Miscellaneous | 2,480,635 | 0.21 | 8,062.06 |
| Other | 24,790,490 | 2.13 | 80,569.09 |
| Ponds | 2,543,000 | 0.22 | 8,264.75 |
| Pumping station | 520,348 | 0.04 | 1,691.13 |
| Water supply | 5,753,928 | 0.49 | 18,700.27 |
| Waterlogged land works | 6,166,250 | 0.53 | 20,040.31 |
| Wells | 1,940,864 | 0.17 | 6,307.81 |
| Total | 349,026,911 | 29.95 | 1,134,337.46 |
| Forestry (including approximately 360,000 hectares of forest plantation) |
| Forest plantation (nursery) | 5,393,785 | 0.46 | 17,529.80 |
| Forest plantation (production) | 39,230,285 | 3.37 | 127,498.43 |
| Forest plantation (protection) | 182,025,511 | 15.62 | 591,582.91 |
| Miscellaneous | 10,889,056 | 0.93 | 35,389.43 |
| Other | 16,110,250 | 1.38 | 52,358.31 |
| Plantation fodder | 500,000 | 0.04 | 1,625.00 |
| wells | 292,500 | 0.03 | 950.63 |
| Total | 254,441,387 | 21.84 | 826,934.51 |

| Fishery |  |  |  |
| --- | --- | --- | --- |
| Canals | 9,444,700 | 0.81 | 30,695.28 |
| Dams (tidal) | 3,505,783 | 0.30 | 11,393.79 |
| Dikes (perimeter) | 467,500 | 0.04 | 1,519.38 |
| Infrastructure | 14,873,112 | 1.28 | 48,337.61 |
| Miscellaneous | 138,000 | 0.01 | 448.50 |
| Other | 1,975,000 | 0.17 | 6,418.75 |
| Ponds | 116,053,500 | 9.96 | 377,173.88 |
| Pumping station | 538,633 | 0.05 | 1,750.56 |
| Total | 146,996,228 | 12.61 | 477,737.74 |
| Dairy |  |  |  |
| Infrastructure | 15,255,538 | 1.31 | 49,580.50 |
| Loans for development | 2,692,154 | 0.23 | 8,749.50 |
| Total | 17,947,692 | 1.54 | 58,330.00 |
| Road Construction |  |  |  |
| Road construction | 55,064,856 | 4.73 | 178,960.78 |
| Total | 55,064,856 | 4.73 | 178,960.78 |
| Training |  |  |  |
| Training | 29,462,811 | 2.53 | 95,754.14 |
| Training (health) | 550,000 | 0.05 | 1,787.50 |
| Training (literacy) | 19,956,420 | 1.71 | 64,858.37 |
| Training (literacy) - School feeding | 34,568,880 | 2.97 | 112,348.86 |
| Total | 84,538,111 | 7.25 | 274,748.86 |
| Drinking Water Supply |  |  |  |
| Drinking water supply | 8,309,299 | 0.71 | 27,005.22 |
| Infrastructure | 8,725,800 | 0.75 | 28,358.85 |
| Other | 8,599,600 | 0.74 | 27,948.70 |
| Sanitation | 262,295 | 0.02 | 852.46 |
| Water supply | 8,397,522 | 0.72 | 27,291.95 |
| Total | 34,294,516 | 2.94 | 111,457.18 |

Annex 5 – WFP Projects Profiles with Activities and Food Utilisation (1979-2005)

Annex 6

Chart -From Sector Interventions to Integrated Rural Development

Annex 7 – Map – WFP Resources per Province (1979 – 2005)

# Footnotes

Enabling Development: Document WFP/EB.A/99/4-A, dated 13 December 2001.  Gender Policy (2003-2007): Enhanced Commitments to Women to Ensure Food Security.  Document WFP/EB.3/2002/4-A, dated 26 September 2002.

Composed of Sylvie Dideron, Socio-Economist, Consultant; Pernille Hougesen, Evaluation Officer, WFP, Rome; Gilbert Landart, Mission Leader, FAO, Rome; Henri Loze, Soil Conservation and Irrigation Specialist, Consultant; Cui Shuli, Women in Development Specialist, Local Consultant. From the WFP Country Office, Kate Milliken and Luo Shenglian have participated in the mission work in the field.

See figures in Annex 2.

In addition, between 1984 and 1998 four Quick Action projects worth US$5 million were launched to assist with various emergencies. In 1998, EMOP 6045 worth US$93 million was approved to assist flood affected people in Anhui, Hubei, Hunan, and Jianxi. An evaluation of this operation was undertaken in 2000. WFP/EB.2/2000/3/1.

In 1979, agricultural and economic reforms were launched in China. A major innovation was the allocation of arable land use rights to individual farmers on the basis of the number of people in the family. This was accompanied by a progressive shift from State governed marketing of agricultural products to the open market.

Proposals will be discussed during various workshops with project staff, confronted with household interviews and community based PRA sessions. Project design is still however de facto concentrated within the hands of the county PMOs. VIGs (Village Implementation Groups) are instrumental to the PRA design. Each VIG is supposed to define a VDP (Village Development Plan), which needs to be improved both in scope (so that VDP is not a mere transcription of County or Township level development plans) and visibility (effective ownership of the plan by the VIG).

Located in the north-west part of China, it covers an overall area of 631,000 km2, where erosion and soil losses are extensive, threatening population livelihood and accelerating the process of sedimentation of the Yellow River which in turn accentuates the danger of flood disasters.

See, in particular, Sectoral Evaluation of WFP-assisted activities for the Development and Protection of Rainfed Agriculture in China (Loess Plateau). May-June 1992.

Projects 2697 and 3355.

2633 Hongze Lake, 2700 Hnagzou Bay, 2730 Tianjin fish and fodder production, 2771 Shrimp farms at Bohai Bay on the East cost.

2,772 in Liaoning, 2,605 in Ningxia Hui and 2,811 in Hebei.

The establishment costs could have been reduced if a less intensive soil preparation and lower tree density on plantations had been used and more focus on maintenance and tree thinning.

E.g. Comprehensive Development Programme of the Loess Plateau in the 80’ and 90’, Development of Western China in the late 90s and 2000s.

Gansu Rural Integrated Development Programme.

Report on WFP/IFAD Collaboration in China, prepared by Alice Carloni, Team Leader, Lubiao Zhang, Local Consultant, and Liu Dageng, IFAD Focal Point (WFP Country Office staff) – 2001.

World Bank is currently implementing a Poverty Alleviation Programme in some of WFP counties in Gansu.

WFP/EB.1/2001/8/1.

The rations distributed are family rations thus benefiting the HH of the person participating in the given activity. Based on initial VAM report, HH are estimated to have 4 members on average.

Source: Country Office. As per design, WFP targeted the same HH for both FFT and FFW but in different years; husband, wife or both have participated, but are only counted once as beneficiaries.

In 'Evaluation the WFP “Enabling Development” Policy' – November 2004 – DRN led consortium.

Country Programme – China (2001-2005) – WFP/EB/2001/8/1, page 8, para. 19.

However, the CSO presented food gaps of 5 to 6 months in the remote mountainous where WFP's interventions had to be in line with the VAM recommendations.

In 'Evaluation the WFP “Enabling Development” Policy' – November 2004 – DRN led consortium.

This analysis is based on the latest available statistical data from the NSB and the inclusion of additional physical type indicators generated through GIS imagery analysis.

Vulnerability analysis of Chinese counties – June 2003 – WFP-IFAD China VAM unit.

Mainly other World Bank poverty alleviation projects or fragile resource based development projects.

The assumption has been that staffing to ensure and follow-up the implementation of VDPs and to accompany and support the VIGs is everywhere forthcoming and that multiplying the number of PMOs at county and townships would be sufficient to cater with the management of the project.

US$1 = 8.3 Yuan Renminbi (CNY) in June 2005.

The WFP-assisted projects in these two provinces were visited by the evaluation mission.

One explanation could be that during one of the two project years (2004) no activity (output and work load mobilized) was reported under these activities, and an error could have thus occurred during compilation.

Such as those with terracing (very high gradient used, removal of top soil norm of 20 m³ a day, no biological stabilization), concrete catchment areas for drinking water tanks but plastic sheets seen in the field, irrigation tanks or cisterns built and designed without provisions for water harvesting canals or improved connections to natural ravines or springs. Some norms seem too low (biogas tanks, livestock stalls if minimum husbandry specifications are to be adhered to).

The most important is with terracing in the West Guangxi project where the average per ha work norm is 4,950 work days per ha (compared to 2,950 in Yunnan in similar red soil Karstic conditions).

Some basic calculation have been presented in the IFAD working papers for activities such as water tanks, canals etc. where a bill of quantities was made and average work norms calculated.

For example, different tasks are needed to build a terrace: (a) surface soil stripping and storing; (b) land levelling and modelling for water conservation; (c) construction of edge or retention wall; (d) return of stored top soil; and (e) vegetalization or stabilization of terrace edge or ridge. Each terrace is different in size, in gradient and before knowing the exact location of the area to be treated, it is impossible to assess a precise work load.

This study was undertaken in the period of 31 October-21 November 2001.

Report on WFP/IFAD Collaboration in China, prepared by Alice Carloni, Team Leader, Lubiao Zhang, Local Consultant, and Liu Dageng, IFAD Focal Point (WFP Country Office staff).

World Bank is currently implementing a Poverty Alleviation Programme in some of WFP counties in Gansu.

An interesting feature is that for social construction there seems to have been more food distributed per beneficiary than the other activities. This is the same in Shanxi and in Shaanxi and Hubei. The team discussed this at provincial level and following explanations were offered; it could be explained by limited number of household with available labour being compensated by allocating more workdsays to the same participant. Another explanation could be that the actual number of household members sometimes turn out to be less than the planned 5 members due to the one child policy, thus less beneficiaries share the same food.

A fund composed by returned premiums from insurance companies.

In order to reduce the delay in food deliveries WFP is currently reviewing WFP’s business process piloting a new programming procedure that in short allows the country office to make commitments based on a (presumed) donor pledge.

The cash is for non food inputs (construction materials, skilled labour and supervision and training materials, training of trainers and salary for the trainers, etc.).

Source: CO. The total figure is higher, but unfortunately  the CO was not able to complete figures at the time of writing.

Conversion rate is 0.7.

In 'Evaluation the WFP “Enabling Development” Policy' – November 2004 – DRN led consortium.

Julian Lefevre,Chief Evaluation Officer, OEDE/WFP.

July 15, 2004/Revised July 20, 2004. Further revision on January 11, 2005.

Although it should be noted that 1999 deliveries reached a new peak of 370,372 tons due to large shipments for the flood EMOP, no. 6045.

Enabling Development: Document WFP/EB.A/99/4-A, dated 13 December 2001. Gender Policy (2003-2007): Enhanced Commitments to Women to ensure food security. Document WFP/EB.3/2002/4-A dated 26 September 2002.

Capacity building is the fifth of WFP’s five new corporate Strategic Priorities, namely “Helping governments establish and manage national food assistance programmes”. See the Strategic Plan (2004-2007) – document WFP/EB.3/2003/4-A/1 dated 15 October 2002.

For reference, see the PR China “Country Case Study on Good Practices and Insights/Lessons from the Operationalization of WFP’s Commitments to Women (1996-2001) and Input to WFP’s Gender Strategy (2003-2007) and Enhanced Commitments to Women” – Rome, January 2002.

The division of responsibilities with regard to the key issues is tentative and may be amended by the team leader in consultation with the team members, depending on the skills sets and interests of individual team members.

# Text boxes

Areas of project intervention

A	Area where WFP has supported the conversion of dry-land to paddy fields and where farmers  either already possess or have been supported to construct water tanks to store rain water over winter.

B	Area where WFP has supported dry land improvement on sloped land and provided a water tank.

Areas of additional intervention

C	Area where additional improvements could have been supported, idem on the other side of the valley where some farmers (D) have constructed small ridges to plant tree crops and vegetables.

In addition to productive activities, a series of wider community based activities could have been implemented: i.e.

- improve the overall sanitation within the community, i.e. market place, paths within and between the houses, waste water sanitation etc to avoid the hamlet to become a mud pool during rainy seasons (E);

- improve access to the community, in this case by upgrading the rural access track, in other cases by developing 'people friendly' sloped paths (F);

- work in addition to ecological tree plantations on plugging the major gullies in the landscape.

Integrated Rural Development

- Introduction and gradual development of PRA and focusing on household food security.

- Opening to more human resource development and social activities.

- Stronger gender focus.

Integrated Agriculture Development

- Concentrated area based approach and integration of various sectors.

- Minimum additional social activities such as literacy, training and water supply.

- Little gender focus.

Conservation, 18.66%

Soil and Water

Dryland Development -

Forestry, 21.84%

Fishery, 12.61%

29.95%

Irrigation and Drainage,

Training, 7.25%

Other, 9.69%

(1997/05)

Development

Integrated Rural

(1991/96)

Integrated

Agricultural

Development

(1982/90)

Sectoral Assistance

(1979/81)

Quick Action

Emergency and

Millions US$

700

600

500

400

300

200

100

0

Sector

- Strong sector based but with some supporting social infrastructures.

- Work for collective assets.

- Little household and no gender focus.